## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Matigara | Siliguri W/S Division | Khoklong Piped Water Supply Scheme | SM/13437 | New | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 2038/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 12.83 | 0 | 0 | 0
2 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHOKLONG PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 1674/NMD | 29/09/2023 | 29/10/2023 | B.B. CONCERNED | 11.43 | 8.78 | 76.86 | 70
3 | DARJEELING | Matigara | Siliguri W/S Division | Khoklong Piped Water Supply Scheme | SM/13437 | New | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH PROPOSED KHOKLONG PIPED WATER SUPPLY SCHEMES AT THE UNCOVERED MOUZAS UNDER MATIGARA BLOCK OF SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000066/2023-2024 | 259/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.02 | 2.02 | 100 | 100
4 | DARJEELING | Matigara | Siliguri W/S Division | Khoklong Piped Water Supply Scheme | SM/13437 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 79/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 1.08 | 0 | 0 | 0
5 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | Infrastructure development cost for new service connection at KHUKHLUNG PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 100000115666 Reference ID : 860308376 |  |  | BILL/00980/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.39 | 0 | 0 | 0
6 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | Power Service connection charges at T.W No-II of Khoklong PWSS under Northern Mechanical Division dist. Darjeeling CONSUMER ID:- 403230623 |  |  | BILL/00528/2024-2025 | BP/24-25/130 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.9 | 0 | 0 | 0
7 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | New Service Connection Charge for new service connection at KHUKHLUNG PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 4003460490 Reference ID : 403255264 |  |  | BILL/00973/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
8 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | New Service Connection Charge for KHOKLONG, T/W No.I, under MATIGARA CCC, [APPLICATION NO. 4003316039, Reference ID : 403143725] |  |  | BILL/01952/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.35 | 0 | 0 | 0
9 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000995/2024-2025 | 14/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0 | 0
10 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
11 | DARJEELING | Matigara | Northern Mechanical | Khoklong Piped Water Supply Scheme | SM/13437 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001065/2024-2025 | 33/NMD | 06/01/2025 | 05/02/2025 | SAIKAT SINHA | 12.3 | 0 | 0 | 0
Total | [13 empty] | 176.19 | 10.8 | 6.13