## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Matigara | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme | SM/13438 | New | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 2039/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 15.3 | 0 | 0 | 0
2 | DARJEELING | Matigara | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme | SM/13438 | New | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH PROPOSED NICHITPUR PIPED WATER SUPPLY SCHEMES AT THE UNCOVERED MOUZAS UNDER MATIGARA BLOCK OF SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000067/2023-2024 | 260/SSD | 05/06/2023 | 15/06/2023 | SUBHANKAR GHOSH | 2.05 | 0 | 0 | 100
3 | DARJEELING | Matigara | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme | SM/13438 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 2302/SWSD | 12/12/2023 | 12/12/2023 | Resource Division | 2.75 | 0 | 0 | 0
4 | DARJEELING | Matigara | Northern Mechanical | Nichitpur Piped Water Supply Scheme | SM/13438 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NICHITPUR PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000818/2023-2024 | 1673/NMD | 29/09/2023 | 29/10/2023 | M/S UTPAL CHAKRABORTY & CO. | 11.43 | 0 | 0 | 85
5 | DARJEELING | Matigara | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme | SM/13438 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 71/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 1.29 | 0 | 0 | 0
6 | DARJEELING | Matigara | Northern Mechanical | Nichitpur Piped Water Supply Scheme | SM/13438 | New | New Service Connection Charge for NICHITPUR, T/W No. II, under NAXALBARI CCC, [APPLICATION NO. 4003299652, Reference ID : 403130074] |  |  | BILL/01953/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.95 | 0 | 0 | 0
7 | DARJEELING | Matigara | Northern Mechanical | Nichitpur Piped Water Supply Scheme | SM/13438 | New | New Service Connection Charge for NICHINTAPUR, T/W No. I, under MATIGARA CCC [APPLICATION NO. 4003299595 ; Reference ID : 403130071] |  |  | BILL/01816/2023-2024 | BP/23-24/276 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.83 | 0 | 0 | 0
8 | DARJEELING | Matigara | Central Drilling | Nichitpur Piped Water Supply Scheme | SM/13438 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | DARJEELING | Matigara | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme | SM/13438 | New | Laying distribution pipeline and Rising Main allied with construction of 2 nos. big dia rig bore tube well by ODEX-165, Pump House (5.4 X 3.65 m), Iron Elimination Plant (10 cu.m/hr.), Boundary Wall including FHTC at NICHITPUR Piped Water Supply Scheme under Matigara Block, Darjeeling Dist. in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000039/2023-2024 | 643/SWSD | 15/06/2023 | 11/05/2025 | U.K CONSTRUCTIONS | 108.96 | 0 | 0 | 30
10 | DARJEELING | Matigara | Northern Mechanical | Nichitpur Piped Water Supply Scheme | SM/13438 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000995/2024-2025 | 14/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0 | 0
11 | DARJEELING | Matigara | Northern Mechanical | Nichitpur Piped Water Supply Scheme | SM/13438 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
Total | [13 empty] | 21629.36 | 0 | 0