## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Naxalbari | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13439 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Dalkajhar Forest Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. |  | Junior Engineer (Civil) | ORD/000154/2022-2023 | 273/SSD | 20/05/2022 | 09/06/2022 | SUBHANKAR GHOSH | 2.26 | 2.26 | 100 | 100
2 | DARJEELING | Naxalbari | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13439 | New | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 2052/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 0.87 | 0 | 0 | 0
3 | DARJEELING | Naxalbari | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13439 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 61/SWSD | 09/01/2024 | 09/01/2024 | Resource Division | 0.94 | 0 | 0 | 0
4 | DARJEELING | Naxalbari | Northern Mechanical | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13439 | New | Quotation for new service Connection at T.W No- I of Dalkajhar Forest w/s scheme. |  |  | BILL/00321/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.53 | 0 | 0 | 0
5 | DARJEELING | Naxalbari | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13439 | New | Laying of distribution pipeline and Rising Main allied with construction of 1 no. big dia rig bore tube well by ODEX-165, Pump House (5.4 X 3.60 m), Iron Elimination Plant (10 cu.m./hr.), Boundary Wall including FHTC at DALKAJHAR FOREST Piped Water Supply Scheme under Naxalbari block, Darjeeling dist. in connection with Jal Jeevan Mission under Siliguri Sub Division,, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000041/2023-2024 | 1041/SWSD | 27/07/2023 | 12/01/2026 | SUDIP BASAK | 59.15 | 0 | 0 | 50
6 | DARJEELING | Naxalbari | Northern Mechanical | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13439 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 1374/NMD | 09/08/2023 | 04/04/2025 | SAIKAT SINHA | 10.66 | 7.37 | 69.12 | 100
Total | [13 empty] | 79.4 | 9.62 | 12.12