## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Naxalbari | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | New | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 2021/SWSD | 15/12/2022 | 15/12/2022 | Resource Division | 2.39 | 0 | 0 | 0
2 | DARJEELING | Naxalbari | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Manja Tea Garden Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000322/2022-2023 | 312/SSD | 14/06/2022 | 04/07/2022 | ENVIROTECH SOLUTIONS | 2.28 | 2.12 | 92.77 | 100
3 | DARJEELING | Naxalbari | Northern Mechanical | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | New | New Service Connection Charge for MANJHA T.G., T.W. No. I under NAXALBARI CCC, [APPLICATION NO. 4003194643, Reference ID : 403046929] |  |  | BILL/00595/2023-2024 | BP/23-24/79 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.19 | 0 | 0 | 0
4 | DARJEELING | Naxalbari | Northern Mechanical | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | New | New Service Connection Charge for MANJHA T.G., T.W. No. III under NAXALBARI CCC, [APPLICATION NO. 4003194667, Reference ID : 403046932] |  |  | BILL/00594/2023-2024 | BP/23-24/79 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.87 | 0 | 0 | 0
5 | DARJEELING | Naxalbari | Northern Mechanical | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | New | New Service Connection Charge for MANJHA T.G., T.W. No. II under NAXALBARI CCC, [APPLICATION NO. 4003194663, Reference ID : 403046923] |  |  | BILL/00596/2023-2024 | BP/23-24/79 | 11/08/2023 | 11/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0 | 0
6 | DARJEELING | Naxalbari | Northern Mechanical | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ,(Zone-I) TW No. I and (Zone-II) TW No. I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000168/2023-2024 | 1210/NMD | 26/07/2023 | 25/08/2023 | M/S PALIDEB ENGINEERING WORKS | 23.21 | 22.6 | 97.38 | 100
7 | DARJEELING | Naxalbari | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 87/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 3.3 | 0 | 0 | 0
8 | DARJEELING | Naxalbari | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | New | Laying distribution system along with construction of pump houses with toilet, boundary walls at tube well sites, laying of rising main, providing FHTC with platform and other allied works under Jal Jeevan Mission (JJM) for MANJHA TEA GARDEN Piped Water Supply Scheme under Naxalbari block, Darjeeling District under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000271/2022-2023 | 2504/SWSD | 10/02/2023 | 31/12/2023 | BUDDHADEV NAG | 154.25 | 122.58 | 79.47 | 90
9 | DARJEELING | Naxalbari | Northern Mechanical | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MANJHA TEA GARDEN PWSS at TW NO II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001617/2023-2024 | 661/NMD | 15/03/2024 | 02/01/2025 | SARKAR ELECTRIC | 11.88 | 11.22 | 94.46 | 100
Total | [13 empty] | 211.05 | 158.52 | 75.11