## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Pathar Hirhirar Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. |  | Junior Engineer (Civil) | ORD/000161/2022-2023 | 307/SSD | 09/06/2022 | 29/06/2022 | SUBHANKAR GHOSH | 3.09 | 3.06 | 99.03 | 100
2 | DARJEELING | Phansidewa | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 2044/SWSD | 16/12/2022 | 16/12/2022 | Resource Division | 30.96 | 0 | 0 | 0
3 | DARJEELING | Phansidewa | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | Construction of 200 Cu.M. capacity RCC Elevated Reservoir of 20 mtr. Staging Height with laying distribution system, soil investigation, rising main, boring of deep tubewells by ODEX-165, construction of pump houses with toilet, boundary wall at head works 2nd tubewell & 3rd Tubewell sites with necessary interconnection, providing FHTC with platform with other allied works under Jal Jeevan Mission for PATHAR HIRHIRAR CHHAT piped W/S scheme of Phansidewa Block under Siliguri Sub Division PHE Dte. ( Sl No. 08) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000075/2023-2024 | 859/SWSD | 12/07/2023 | 16/08/2026 | SUBIR CH. CHOWDHURY | 403.68 | 249.1 | 61.71 | 70
4 | DARJEELING | Phansidewa | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 68/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 8.57 | 0 | 0 | 0
5 | DARJEELING | Phansidewa | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | New Service Connection Charge for PATHAR HARHARIAR CHHAT, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003299733 ; Reference ID : 403131317] |  |  | BILL/01739/2023-2024 | BP/23-24/224 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.72 | 0 | 0 | 0
6 | DARJEELING | Phansidewa | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | New Service Connection Charge for PATHAR HIRHIRAR CHHAT , T/W No. III, under NAXALBARI CCC, [APPLICATION NO. 4003313525, Reference ID : 403145696] |  |  | BILL/01954/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.79 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | New Service Connection Charge for PATHAR HARHARIAR CHHAT, T/W No. II, under NAXALBARI CCC [APPLICATION NO. 4003300848 ; Reference ID : 403131314] |  |  | BILL/01740/2023-2024 | BP/23-24/225 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.46 | 0 | 0 | 0
8 | DARJEELING | Phansidewa | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHAR HIRHIRAR CHHAT PIPED WATER SUPPLY SCHEME, TW No. I, II and III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000780/2023-2024 | 1644/NMD | 29/09/2023 | 13/04/2025 | PADMA ENGINEERING CO. | 20.85 | 0 | 0 | 90
9 | DARJEELING | Phansidewa | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001071/2024-2025 | 39/NMD | 06/01/2025 | 05/02/2025 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0 | 0
10 | DARJEELING | Phansidewa | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000996/2024-2025 | 15/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0 | 0
11 | DARJEELING | Phansidewa | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 10/11/2025 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
Total | [13 empty] | 678.96 | 252.16 | 37.14