## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Singijhor Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000327/2022-2023 | 409/SSD | 28/07/2022 | 17/08/2022 | ENVIROTECH SOLUTIONS | 3.6 | 3.6 | 100 | 0
2 | DARJEELING | Phansidewa | Central Drilling | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 12.39 | 0.06 | 11
3 | DARJEELING | Phansidewa | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | Construction of 300 - 1 No. & 150 - 2 Nos. cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site (Zone - I, II & III) including distribution system (HDPE) with Rising Main, Rig bore 6 Nos. big dia T/W by Odex-165 method, Providing Functional Household Tap Connection (FHTC), Pump House 6 Nos., Blower Room 3 Nos., IEP 70, 35 & 35 cu.m./hr, Boundary Walls, Horizontal Boring, Soil Testing and allied works at SINGHIJHOR PWSS Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000107/2023-2024 | 1147/SWSD | 08/08/2023 | 01/07/2025 | UNIBRO INFRASERV PRIVATE LIMITED | 1080.94 | 0 | 0 | 50
4 | DARJEELING | Phansidewa | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SINGIJHOR PIPED WATER SUPPLY SCHEME, ( ZONE-I) TW No. I and II, (ZONE-II) TW No. I and II, (ZONE-III) TW No. I and II, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000790/2023-2024 | 1654/NMD | 29/09/2023 | 30/08/2025 | M/S P.P. ELECTRICALS | 45.94 | 34.25 | 74.56 | 75
5 | DARJEELING | Phansidewa | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | Supply and Delivery of C.I.D.F specials for using pumping machinery installation purpose at SINGIJHORA W/S/S under JJM in the dist. of Siliguri under, Northern Mechanical Division ,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001437/2023-2024 | 425/SMSD | 20/12/2023 | 31/12/2024 | SARKAR ELECTRIC | 0.58 | 0 | 0 | 100
6 | DARJEELING | Phansidewa | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 2201/SWSD | 04/01/2023 | 04/01/2023 | Resource Division | 74.03 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 58/SWSD | 09/01/2024 | 09/01/2024 | Resource Division | 22.63 | 0 | 0 | 0
8 | DARJEELING | Phansidewa | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | New Service Connection Charge for SINGIJHOR Zone-II,TW- I under BAGDOGRA CCC |  |  | BILL/00384/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 17.12 | 0 | 0 | 0
9 | DARJEELING | Phansidewa | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | New service connection at singijhora PWSS,Z-I,TW-II under NMD PHE Dte. Application no- 4003417642 Ref id- 403224817 |  |  | BILL/00386/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 19.19 | 0 | 0 | 0
10 | DARJEELING | Phansidewa | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | New Service Connection Charge for SINGIJHOR Zone-II,TW- II under BAGDOGRA CCC |  |  | BILL/00383/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.76 | 0 | 0 | 0
11 | DARJEELING | Phansidewa | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | New Service Connection Charge for SINGIJHORA, T/W No.I, ZONE-III under BAGDOGRA CCC, [APPLICATION NO. 4003326146, Reference ID : 403152620] |  |  | BILL/01958/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.79 | 0 | 0 | 0
12 | DARJEELING | Phansidewa | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | New Service Connection Charge for SINGIJHORA, T/W No.II, ZONE-III under BAGDOGRA CCC, [APPLICATION NO. 4003326171, Reference ID : 403152622] |  |  | BILL/01959/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.05 | 0 | 0 | 0
13 | DARJEELING | Phansidewa | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | New | New service connection at singijhora PWSS,Z-I,TW-I under NMD PHE Dte. Application no- 4003417637 Ref id- 403224816 |  |  | BILL/00387/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.08 | 0 | 0 | 0
Total | [13 empty] | 22646.48 | 50.24 | 0.22