## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. | SM/14517 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 2198/SWSD | 04/01/2023 | 04/01/2023 | Resource Division | 124.88 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. | SM/14517 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 2286/SWSD | 11/12/2023 | 11/12/2023 | Resource Division | 5.18 | 0 | 0 | 0
3 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. | SM/14517 | Augmentation | New Service Connection Charge for MATIGARAHAT, T/W No.I,ZONE-III under MATIGARA CCC, [APPLICATION NO. 4003316052, Reference ID : 403143727] |  |  | BILL/01961/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.19 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. | SM/14517 | Augmentation | New Service Connection Charge for MATIGARAHAT, T/W No. II, ZONE-III under MATIGARA CCC, [APPLICATION NO. 4003316072, Reference ID : 403143728] |  |  | BILL/01960/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.65 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. | SM/14517 | Augmentation | Construction Of 500 -1no & & 600 -1 No & 450 -1 No Cu.M. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site ( Zn-I, Zn-II & Zn-III) including distribution system (UPVC) with Rising Main,Providing Functional Household Connection (FHTC) , Pump House 4 Nos, ,Boundary Walls , Horizontal boring and allied works for Augmentation of MATIGARAHAT PWSS, Matigara block under Siliguri Sub Division.P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000099/2023-2024 | 1082/SWSD | 02/08/2023 | 01/08/2025 | SRINIWAS AGARWAL | 2266.88 | 775.08 | 34.19 | 70
6 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. | SM/14517 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME, (Zone-II) TW No. I and (Zone-III) TW No. I, II and III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000755/2023-2024 | 1583/NMD | 08/09/2023 | 01/10/2025 | ANUP BASU | 50.02 | 0 | 0 | 25
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. | SM/14517 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001066/2024-2025 | 34/NMD | 06/01/2025 | 05/02/2025 | PRATIK ROY | 9.2 | 0 | 0 | 0
Total | [13 empty] | 2476.01 | 775.08 | 31.3