## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | SM/14834 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 206/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 1.59 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | SM/14834 | Augmentation | Construction the boring of Odex-165 tubewell, laying distribution, iron elimination plant, pump house boundary wall, TW all complete for Augmentation of Bairagi Piped Water Supply Scheme under Kharibari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000043/2023-2024 | 653/SWSD | 15/06/2023 | 10/05/2024 | NARAYAN CH GHOSH | 66.78 | 22 | 32.95 | 45
3 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | SM/14834 | Augmentation | Quotation Charges for New Service Connection at Bairagi PWSS,TW-I under NMD PHE Dte. Application No- 4003340167 Ref ID- 403162856 |  |  | BILL/01009/2024-2025 | BP/24-25/167 | 29/08/2024 | 29/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.69 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | SM/14834 | Augmentation | Laying distribution of HDPE pipe line, sluice valve chamber, construction of boundary wall including drain & paver block pathway for Augmentation at Bairagi Water Supply Scheme, 2nd tubewell site of Khoribari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000040/2023-2024 | 644/SWSD | 15/06/2023 | 05/05/2025 | M/S SHIVAJI ROY | 22.4 | 7.43 | 33.15 | 40
Total | [13 empty] | 100.46 | 29.43 | 29.29