## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | SM/14834 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 206/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 1.59 | 0 | 0 | 0
2 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | SM/14834 | Augmentation | Quotation Charges for New Service Connection at Bairagi PWSS,TW-I under NMD PHE Dte. Application No- 4003340167 Ref ID- 403162856 |  |  | BILL/01009/2024-2025 | BP/24-25/167 | 29/08/2024 | 29/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.69 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | SM/14834 | Augmentation | Laying distribution of HDPE pipe line, sluice valve chamber, construction of boundary wall including drain & paver block pathway for Augmentation at Bairagi Water Supply Scheme, 2nd tubewell site of Khoribari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000040/2023-2024 | 644/SWSD | 15/06/2023 | 05/05/2025 | M/S SHIVAJI ROY | 22.4 | 0 | 0 | 40
4 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | SM/14834 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000450/2023-2024 | 1389/NMD | 09/08/2023 | 12/03/2025 | M/S ANJALI ENTERPRISE | 12.38 | 0 | 0 | 100
Total | [13 empty] | 46.06 | 0 | 0