## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | SM/14835 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 208/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 1.59 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | SM/14835 | Augmentation | CONSTRUCTION OF HOUSE HOLD TAP CONNECTION (FHTC) AT DIFFERENT MOUZAS UNDER DIFFERENT PIPED WATER SUPPLY SCHEME (PART -C) IN CONNECTION WITH JAL JEEVAN MISSION UNDER SILIGURI W/S DIVISION P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000162/2023-2024 | 364./SSD | 10/08/2023 | 24/09/2023 | SEBU CHAKRABORTY | 0.98 | 0.91 | 92.64 | 100
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | SM/14835 | Augmentation | Construction of household tap connection (FHTC)at different mouzas under different piped water supply scheme (Part A) in connection with Jal Jeevan Mission under Siliguri W/S Division P.H.E DTE. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000157/2023-2024 | 364/SSD | 10/08/2023 | 24/09/2023 | SEBU CHAKRABORTY | 0.98 | 0.91 | 92.94 | 100
4 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | SM/14835 | Augmentation | Quotation for new service connection at Damdama w/s scheme T.W N0_ I in the dist. Darjeeling |  |  | BILL/00322/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.81 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | SM/14835 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME, TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000442/2023-2024 | 1381/NMD | 09/08/2023 | 02/04/2025 | ASHWIRBAD WOOD CRAFT | 10.38 | 8.57 | 82.59 | 85
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | SM/14835 | Augmentation | Acceptance cum work order for Laying of rising main, distribution system of pipe line, construction of pump house, boundary wall, sinking of rig bore deep tube well by ODEX-165 method of drilling, development of land and othar works for Augmentation of Damdama nPiped W/S Scheme within Naxalbari Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000194/2023-2024 | 1903/SWSD | 11/10/2023 | 29/03/2025 | K.K.GHOSH & CO. | 31.94 | 17.02 | 53.3 | 85
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | SM/14835 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | SM/14835 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001067/2024-2025 | 35/NMD | 06/01/2025 | 05/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 9.2 | 0 | 0 | 0
Total | [13 empty] | 157.14 | 27.41 | 17.44