## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kharibari | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | SM/14846 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Khunia Pukhari Piped water supply schemes at the uncovered mouzas under Kharibari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000321/2022-2023 | 264/SSD | 18/05/2022 | 07/06/2022 | ENVIROTECH SOLUTIONS | 3.87 | 3.78 | 97.68 | 0
2 | DARJEELING | Kharibari | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | SM/14846 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 210/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 29.44 | 0 | 0 | 0
3 | DARJEELING | Kharibari | Northern Mechanical | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | SM/14846 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME, TW No.- I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000753/2023-2024 | 1581/NMD | 08/09/2023 | 08/10/2023 | S.G.TECHNICAL SERVICES | 13.8 | 0 | 0 | 0
4 | DARJEELING | Kharibari | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | SM/14846 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 70/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 17.92 | 0 | 0 | 0
5 | DARJEELING | Kharibari | Northern Mechanical | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | SM/14846 | New | New Service Connection Charge for KHUNIA PUKHORI, T/W No. I, under KADAMTALA CCC, [APPLICATION NO. 4003320147, Reference ID : 403147072] |  |  | BILL/01962/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.72 | 0 | 0 | 0
6 | DARJEELING | Kharibari | Northern Mechanical | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | SM/14846 | New | New Service Connection Charge for KHUNIA PUKHORI, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003320195, Reference ID : 403147070] |  |  | BILL/01963/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.82 | 0 | 0 | 0
7 | DARJEELING | Kharibari | Northern Mechanical | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | SM/14846 | New | Additional Charges For New service connection at Khunia Pukhori pwss TW-II under NMD PHE Dte. Application no- 4003320195 Ref id- 860301418 |  |  | BILL/00385/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0 | 0
8 | DARJEELING | Kharibari | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | SM/14846 | New | Construction of 350 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site including distribution system (HDPE) with Rising Main, Rig bore 2 nos. big dia T/W by Odex-165 method, Providing Functional Household Connection (FHTC), Pump Houses 2 Nos., Blower Room, IEP 70 cu.m./hr., Boundary Walls, Soil Testing and allied works at KHUNIA PUKHARI PWSS, Kharibari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000119/2023-2024 | 1211/SWSD | 11/08/2023 | 01/10/2025 | THE TEESTA CONSTRUCTION | 667.04 | 61.49 | 9.22 | 70
Total | [13 empty] | 743.43 | 65.27 | 8.78