## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 201/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 1.59 | 0 | 0 | 0
2 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000806/2023-2024 | 1663/NMD | 29/09/2023 | 29/10/2023 | SARKAR ELECTRIC | 10.38 | 10.37 | 99.91 | 100
3 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | Augmentation | New Service Connection Charge for TARBANDHA, T/W No. II, under BAGDOGRA CCC, [APPLICATION NO.4003308985, Reference ID : 403137427] |  |  | BILL/02033/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.92 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | Augmentation | New Service Connection Charge for TARBANDHA, T/W No. II, under PHANSIDEWA CCC [APPLICATION NO. 4003303453 ; Reference ID : 403135383] |  |  | BILL/01813/2023-2024 | BP/23-24/273 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.33 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | Augmentation | Laying distribution system along with boring of new tubewells by ODEX-165, construction of pump houses, boundary walls at 3rd and 4th tubewell site, installation of I.E.P. at both sites and other allied works in connection with augmentation of TARBANDHA Piped Water Supply Scheme at Phansidewa block, Darjeeling dist. under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000013/2023-2024 | 336/SWSD | 08/05/2023 | 17/01/2025 | UJJWAL ROY | 90.32 | 57.23 | 63.37 | 75
6 | DARJEELING |  | Central Drilling | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 4.65 | 0.02 | 11
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001072/2024-2025 | 40/NMD | 06/01/2025 | 05/02/2025 | B.B. CONCERNED | 15.33 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 10/11/2025 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | Augmentation | Additional work (Including repairing of damaged house connection , Pipeline extention of existing pipeline etc) & other allied works(laying of pipeline , cleaning the chokage of pipe line and ferrule , repair of pump house , Drain and boundary wall) in connection with augmentation of TARBANDHA Piped Water Supply Scheme at Phansidewa block, Darjeeling dist. under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000244/2024-2025 | 484/SWSD | 12/02/2025 | 10/12/2025 | UJJWAL ROY | 17.38 | 0 | 0 | 90
Total | [13 empty] | 21639.49 | 72.25 | 0.33