## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Central Drilling | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME | SM/15270 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME | SM/15270 | Augmentation | Acceptance cum work order for laying of rising main, distribution system of pipeline, construction of pump houses, boundary wall, sinking of Rig bore deep tube well by Odex-165 method of drilling, development of land and other allied works for Augmentation of OMI Piped W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. Dist-Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000172/2023-2024 | 1734/SWSD | 22/09/2023 | 26/03/2025 | NARAYAN CH GHOSH | 65.91 | 48.49 | 73.57 | 80
3 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME | SM/15270 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000817/2023-2024 | 1672/NMD | 29/09/2023 | 28/10/2024 | M/S MATRI CONSTRUCTION | 10.37 | 9.37 | 90.31 | 100
4 | DARJEELING |  | Central Drilling | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME | SM/15270 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). (Phase-X) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000031/2024-2025 | 563/CDD | 07/08/2024 | 07/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME | SM/15270 | Augmentation | New Service Connection Charge for OMI, T/W No. II, under NAXALBARI CCC [APPLICATION NO. 4003300005 ; Reference ID : 403131330] |  |  | BILL/01744/2023-2024 | BP/23-24/227 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.79 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME | SM/15270 | Augmentation | New Service Connection Charge for OMI, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003299978 ; Reference ID : 403131329] |  |  | BILL/01743/2023-2024 | BP/23-24/226 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.15 | 0 | 0 | 0
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME | SM/15270 | Augmentation | Acceptance cum Work Order for Additional work (F.H.T.C & LDS) at adjoining mouzas under JJM/Jal Swapna in connection with AUGMENTATION of OMI PIPED WATER SUPPLY SCHEME under Naxalbari block, Darjeeling District under Siliguri W/S Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000008/2025-2026 | 1234/SWSD | 24/04/2025 | 24/05/2025 | NARAYAN CH GHOSH | 2.72 | 0 | 0 | 0
Total | [13 empty] | 21442.74 | 57.86 | 0.27