## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000803/2023-2024 | 1660/NMD | 29/09/2023 | 29/10/2023 | M/S ANJALI ENTERPRISE | 10.08 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 2231/SWSD | 06/01/2023 | 06/01/2023 | Resource Division | 1.97 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1800/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 0.85 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | Augmentation | Acceptance cum work order for installation of the Iron removal filtration plant including platform and drain with necessary connection and blower room 01 No. at Bhalamanshi Piped water supply Scheme H/W Site within Phansidewa Block under Siliguri W/S Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000189/2024-2025 | 3155/SWSD | 25/11/2024 | 25/12/2024 | PALLAB BHOWAL | 26.07 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | Augmentation | Charges for New service Connection at Bhalomanshi TW-II Under NMD,PHE Dte. Application No- 4003425977 Ref. ID- 403232535 |  |  | BILL/00434/2024-2025 | BP/24-25/87 | 18/06/2024 | 18/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.54 | 0 | 0 | 0
6 | DARJEELING |  | Central Drilling | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | Augmentation | Acceptance Cum Work Order for Construction of pump house 2 nos, rig bore 2 nos big dia T/W by ODEX-165 method, boundary walls, laying distribution system (HDPE Pipe), rising main & supplying fabrication on suitable RCC foundation & commissioning with (three) month trial run IEP (30 cu.m/hr-2 nos) and allied works under Augmentation of Bhalamanshi Piped W/S Scheme at Phansidewa block under SSD PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000196/2023-2024 | 1976/SWSD | 26/10/2023 | 29/03/2025 | M/S FULBARI CONSTRUCTION CO. | 92.5 | 0 | 0 | 20
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001072/2024-2025 | 40/NMD | 06/01/2025 | 05/02/2025 | B.B. CONCERNED | 15.33 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 10/11/2025 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
Total | [13 empty] | 21641.58 | 0 | 0