## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Central Drilling | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000807/2023-2024 | 1664/NMD | 29/09/2023 | 29/10/2023 | THE BANERJEE CONCERN | 10.22 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | Acceptance cum Work Order for Construction the boring of ODEX-165 tubewell, laying distribution, iron elimination plant under Augmentation of Purba Bansgaon Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000229/2023-2024 | 2033/SWSD | 06/11/2023 | 21/12/2023 | BUDDHADEV NAG | 55.04 | 6.41 | 11.64 | 17
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | Acceptance cum work order for construction of pump house, boundary wall, drain under Augmentation of Purba Bansgaon Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000182/2023-2024 | 1811/SWSD | 03/10/2023 | 28/08/2025 | AKASH ENTERPRISE | 32.21 | 0 | 0 | 100
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 203/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 0.79 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | Quotation Charges for new Service connection at Purba Bansgaon PWSS , TW-I under NMD PHE Dte. Application No- 4003510209 Ref ID- 403289913 |  |  | BILL/01413/2024-2025 | BP/24-25/240 | 30/10/2024 | 30/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.77 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | Quotation Charges for new Service connection at Purba Bansgaon PWSS , TW-I under NMD PHE Dte. Application No- 4003510161 Ref ID- 403289908 |  |  | BILL/01414/2024-2025 | BP/24-25/240 | 30/10/2024 | 30/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.02 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | New Service Connection Charge for PURBA BANSGAON , T/W No. II, ZONE-II under PHANSIDAWA CCC, [APPLICATION NO. 4003320129, Reference ID : 403147638] |  |  | BILL/01966/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.88 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | New Service Connection Charge for PURBA BANSGAON , T/W No. I, ZONE-II under PHANSIDAWA CCC, [APPLICATION NO. 4003320146, Reference ID : 403147647] |  |  | BILL/01965/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.49 | 0 | 0 | 0
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | Augmentation | Sinking of Rig bored Tubewell by Odex-165 method of drilling & Erection of Iron Elimination Plant of 40 Cum/Hr at 4th TW Site and Construction of Pump House ( 5.40M X 3.65M ) Size with sanitary & plumbing arrangement including Boundary wall along with other anciellary works at 3rd T/W Site for Augmentation of Purba Basgaon Piped Water Supply Scheme within Phansidewa Block under Siliguri W/S Division, related to Jal Jeevan Mission (JJM) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000237/2024-2025 | 350/SWSD | 30/01/2025 | 16/03/2025 | BUDDHADEV NAG | 33.94 | 0 | 0 | 0
Total | [13 empty] | 21507.12 | 6.41 | 0.03