## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15908 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Kuchia Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000328/2022-2023 | 410/SSD | 28/07/2022 | 17/08/2022 | ENVIROTECH SOLUTIONS | 4.2 | 0 | 0 | 0
2 | DARJEELING | Phansidewa | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15908 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 213/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 23.24 | 0 | 0 | 0
3 | DARJEELING | Phansidewa | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15908 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 2292/SWSD | 11/12/2023 | 11/12/2023 | Resource Division | 1.05 | 0 | 0 | 0
4 | DARJEELING | Phansidewa | Northern Mechanical | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15908 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KUCHIA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, & (Zone-II) TW-I, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000813/2023-2024 | 1670/NMD | 29/09/2023 | 29/10/2023 | DIAMOND ELECTRICAL WORKS | 11.6 | 0 | 0 | 60
5 | DARJEELING | Phansidewa | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15908 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 77/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 9.93 | 0 | 0 | 0
6 | DARJEELING | Phansidewa | Northern Mechanical | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15908 | New | New Service Connection Charge for KUCHIA, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003319982, Reference ID : 403147083] |  |  | BILL/01967/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.61 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Northern Mechanical | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15908 | New | Quotation For New Service Connection charges under KUCHIA PWSS Tw-I under NMD PHE dte. Application no- 4003455839 Ref ID-403251521 |  |  | BILL/00620/2024-2025 | BP/24-25/156 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.36 | 0 | 0 | 0
8 | DARJEELING | Phansidewa | Central Drilling | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15908 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21404.74 | 0 | 0