## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Continuation of Hiring of 1 (one) no. diesel consumed vehicle on monthly basis preferably Maxi Cab (with A/C) for O/O the Assistant Engineer, Siliguri Sub Division, P.H.E. Dte. from 01.09.2022 to 30.11.2022 (With Engine Capacity less than or equal to 2000 CC) (Vehicle no. WB 76A4921) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000270/2022-2023 | 439/SSD | 31/08/2022 | 30/11/2022 | SUDIP BASAK | 0.44 | 0.97 | 220.37 | 100
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000052/2023-2024 | 245/SSD | 05/06/2023 | 15/06/2023 | ENVIROTECH SOLUTIONS | 3.87 | 3.86 | 99.61 | 100
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 2199/SWSD | 04/01/2023 | 04/01/2023 | Resource Division | 31.91 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1799/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 33.55 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000288/2023-2024 | 382/SWSD | 15/02/2024 | 16/03/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 5 | 23.17 | 50
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | ISSUE OF FULE FOR OFFICE VEHICLES OF EXECUTIVE ENGINEER SILIGURI W/S DIVISION AND ASSISTANT ENGINEER PHE DTE |  |  | BILL/00354/2023-2024 | BP-2023-24-147 | 09/01/2024 | 09/01/2024 | SONA PETROL PUMP | 0.53 | 0 | 0 | 0
7 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | New Service Connection Charge for BARSADBHITA, T/W No. I, ZONE-II, under KHARIBARI CCC, [APPLICATION NO. 4003319471, Reference ID : 403145974] |  |  | BILL/01969/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.56 | 0 | 0 | 0
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | New Service Connection Charge for BARSADBHITA Zone-III,TW- I under KHARIBARI CCC |  |  | BILL/00382/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.5 | 0 | 0 | 0
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Hiring of (one) no. Disel Motor Cab on daily basis for the Assistant Engineer-II, office of the Executive Engineer, Siliguri W/S Division, P.H.E Dte. |  |  | BILL/00353/2023-2024 | BP-2023-24-154 | 09/01/2024 | 09/01/2024 | SUDIP BASAK | 0.99 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | New Service Connection Charge for BARSADBHITA, T/W No. II, ZONE- II, under KHARIBARI CCC, [APPLICATION NO. 4003319623, Reference ID : 403147073] |  |  | BILL/01968/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.54 | 0 | 0 | 0
11 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site (Zn-II) including distribution system all zones (HDPE) with Rising Main, Rig bore 3 nos. big dia T/W by Odex-165 method (Zn-II, III), Providing Functional Household Connection (FHTC), Pump House 3 Nos., Blower Room, IEP (Zone-III-30, Zn-II 30) cu.m/hr, Boundary Walls, Soil Testing & all repair works at Zone-I & Zn-II and allied works for Augmentation of BARSADVITA PWSS Kharibari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000113/2023-2024 | 1192/SWSD | 10/08/2023 | 01/09/2025 | RAMESH AGARWAL | 572.07 | 345.75 | 60.44 | 60
12 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001070/2024-2025 | 38/NMD | 06/01/2025 | 05/02/2025 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0 | 0
13 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
14 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
15 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BARSADBHITA PIPED, (Zone-II) TW No. I, II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000749/2023-2024 | 1577/NMD | 08/09/2023 | 19/02/2025 | DIPALI CONSTRUCTION | 25.01 | 17.96 | 71.79 | 100
16 | DARJEELING |  | Central Drilling | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 5.4 | 0.03 | 11
Total | [13 empty] | 22207.05 | 378.93 | 1.71