## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kharibari | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Debiganja Piped water supply schemes at the uncovered mouzas under Kharibari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000320/2022-2023 | 261/SSD | 17/05/2022 | 06/06/2022 | ENVIROTECH SOLUTIONS | 3.48 | 3.39 | 97.42 | 0
2 | DARJEELING | Kharibari | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | New | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 2232/SWSD | 06/01/2023 | 06/01/2023 | Resource Division | 23.09 | 0 | 0 | 0
3 | DARJEELING | Kharibari | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1803/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 31.55 | 0 | 0 | 0
4 | DARJEELING | Kharibari | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 80/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 13 | 0 | 0 | 0
5 | DARJEELING | Kharibari | Northern Mechanical | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | New | Quotation For New Service Connection charges under DEBIGANJA PWSS Tw-II under NMD PHE dte. Application no- 4003456575 Ref ID- 403252077 |  |  | BILL/00619/2024-2025 | BP/24-25/156 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0 | 0
6 | DARJEELING | Kharibari | Northern Mechanical | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | New | Quotation For New Service Connection charges under DEBIGANJA PWSS Tw-I under NMD PHE dte. Application no- 4003456573 Ref ID- 403252078 |  |  | BILL/00834/2024-2025 | BP/24-25/157 | 07/08/2024 | 07/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.08 | 0 | 0 | 0
7 | DARJEELING | Kharibari | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | New | Construction of 250 cu.m. capacity R.C.C. Elevated Reservosir, 20 mtrs. Staging Height at the head works site including distribution system (HDPE) with Rising Main, Rig bore 2 nos. big dia T/W by Odex-165 method, Providing Functional Household Connection (FHTC), Pump House 2 Nos., Blower Room, I.E.P. 50 cu.m./hr, Boundary Walls, Soil Testing and allied works at DEBIGANJA PWSS, Kharibari block under Siliguri Sub Division, P.H.E. Dte. . (3rd Call) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000139/2023-2024 | 1411/SWSD | 22/08/2023 | 20/02/2025 | SANJEEV KUMAR | 430.31 | 0 | 0 | 25
8 | DARJEELING | Kharibari | Northern Mechanical | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DEBIGANJA PIPED WATER SUPPLY SCHEME, TW No.- I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000805/2023-2024 | 1662/NMD | 29/09/2023 | 01/07/2025 | PRATIK ROY | 12.92 | 9 | 69.67 | 90
9 | DARJEELING | Kharibari | Central Drilling | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21868.24 | 12.39 | 0.06