## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik,Naxalbari | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Lohasing Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000324/2022-2023 | 402/SSD | 25/07/2022 | 14/08/2022 | ENVIROTECH SOLUTIONS | 2.64 | 2.61 | 98.87 | 30
2 | DARJEELING | Mirik,Naxalbari | Central Drilling | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | DARJEELING | Mirik,Naxalbari | Northern Mechanical | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for LOHASING Piped Water Supply Scheme, TW No.- I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000812/2023-2024 | 1669/NMD | 29/09/2023 | 29/10/2023 | ALPHA ENTERPRISE | 12.03 | 0 | 0 | 0
4 | DARJEELING | Mirik,Naxalbari | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 202/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 23.39 | 0 | 0 | 0
5 | DARJEELING | Mirik,Naxalbari | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 2293/SWSD | 11/12/2023 | 11/12/2023 | Resource Division | 1.88 | 0 | 0 | 0
6 | DARJEELING | Mirik,Naxalbari | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | New | Part Work order for Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging height with Laying distribution system, Soil investigation, Rising main, Boring of deep tubewell by ODEX-165 method, Construction of Pump House with Toilet, Boundary Wall at Head Works and 2nd Tube Well site with necessary interconnection and Providing FHTC and Other allied works under Jal Jeevan Mission for Lohasing Piped water Supply Scheme within Matigara Block under Siliguri W/S Division, P.H.E. Dte. (Part - I) |  |  | ORD/000258/2023-2024 | 109/SWSD | 15/01/2024 | 06/05/2024 | CAPITAL ENGINEERS | 161.7 | 0 | 0 | 0
7 | DARJEELING | Mirik,Naxalbari | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | New | Part Work order for Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging height with Laying distribution system, Soil investigation, Rising main, Boring of deep tubewell by ODEX-165 method, Construction of Pump House with Toilet, Boundary Wall at Head Works and 2nd Tube Well site with necessary interconnection and Providing FHTC and Other allied works under Jal Jeevan Mission for Lohasing Piped water Supply Scheme within Matigara Block under Siliguri W/S Division, P.H.E. Dte. (Part - II) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000196/2024-2025 | 3485/SWSD | 19/12/2024 | 17/02/2025 | CAPITAL ENGINEERS | 87.1 | 0 | 0 | 0
8 | DARJEELING | Mirik,Naxalbari | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 72/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 7.61 | 0 | 0 | 0
9 | DARJEELING | Mirik,Naxalbari | Northern Mechanical | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | New | New Service Connection Charge for LOHASING, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003301385 ; Reference ID : 403131311] |  |  | BILL/01742/2023-2024 | BP/23-24/229 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.31 | 0 | 0 | 0
Total | [13 empty] | 21640.44 | 2.61 | 0.01