## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Naxalbari | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15927 | New | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 2212/SWSD | 05/01/2023 | 05/01/2023 | Resource Division | 11.92 | 0 | 0 | 0
2 | DARJEELING | Naxalbari | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15927 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 2287/SWSD | 11/12/2023 | 11/12/2023 | Resource Division | 4.4 | 0 | 0 | 0
3 | DARJEELING | Naxalbari | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15927 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1804/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 11.72 | 0 | 0 | 0
4 | DARJEELING | Naxalbari | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15927 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Dhemal Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000323/2022-2023 | 319/SSD | 20/06/2022 | 10/07/2022 | ENVIROTECH SOLUTIONS | 2.4 | 0 | 0 | 30
5 | DARJEELING | Naxalbari | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15927 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 73/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 9.99 | 0 | 0 | 0
6 | DARJEELING | Naxalbari | Central Drilling | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15927 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
7 | DARJEELING | Naxalbari | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15927 | New | Construction of Pump House with toilet , laying distribution system, Rising Main, boring of deep tube well by ODEX-165 method, construction of Blower Room with IEP, Boundary Wall at H/W and second tube well site with necessary interconnection and providng FHTC and other allied work under Jal Jeevan Mission for DHEMAL Piped Water Supply Scheme Block : Naxalbari under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000120/2023-2024 | 1225/SWSD | 14/08/2023 | 01/01/2026 | K.R.ENTERPRISE | 349.22 | 0 | 0 | 10
Total | [13 empty] | 21729.42 | 0 | 0