## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME | SM/15928 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Jogibhita Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000329/2022-2023 | 411/SSD | 28/07/2022 | 17/08/2022 | ENVIROTECH SOLUTIONS | 2.76 | 2.7 | 97.83 | 0
2 | DARJEELING | Phansidewa | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME | SM/15928 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 209/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 23.71 | 0 | 0 | 0
3 | DARJEELING | Phansidewa | Central Drilling | JOGIBHITA PIPED WATER SUPPLY SCHEME | SM/15928 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 19/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 6.25 | 9.23 | 10
4 | DARJEELING | Phansidewa | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME | SM/15928 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 81/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 6.67 | 0 | 0 | 0
5 | DARJEELING | Phansidewa | Northern Mechanical | JOGIBHITA PIPED WATER SUPPLY SCHEME | SM/15928 | New | Infrastructure Cost for JOGIBHITA T/W No. I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003323751, Reference ID : 403152325] |  |  | BILL/02034/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.32 | 0 | 0 | 0
6 | DARJEELING | Phansidewa | Northern Mechanical | JOGIBHITA PIPED WATER SUPPLY SCHEME | SM/15928 | New | Infrastructure Cost for JOGIBHITA T/W No. II, under BIDHANNAGAR CCC , [APPLICATION NO. 4003323752, Reference ID : 403152314] |  |  | BILL/02035/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.1 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Central Drilling | JOGIBHITA PIPED WATER SUPPLY SCHEME | SM/15928 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | DARJEELING | Phansidewa | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME | SM/15928 | New | Part Work order for 150 cu.m capacity R.C.C. elevated reservoir, 20 mtrs staging height at the head works site along with distribution system, functional household tap connection, rising main, pump house (2 nos), IEP, boundary wall and tubewell under Jal Jeevan Mission for Jogibhita Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000226/2023-2024 | 1979/SWSD | 26/10/2023 | 01/11/2025 | M/S UTPAL CHAKRABORTY & CO. | 271.29 | 0 | 0 | 25
Total | [13 empty] | 21723.32 | 8.95 | 0.04