## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Purba Bansgaon Chakla Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000330/2022-2023 | 412/SSD | 28/07/2022 | 17/08/2022 | ENVIROTECH SOLUTIONS | 3.69 | 3.69 | 100 | 0
2 | DARJEELING | Phansidewa | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 212/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 23.82 | 0 | 0 | 0
3 | DARJEELING | Phansidewa | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 83/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 12.11 | 0 | 0 | 0
4 | DARJEELING | Phansidewa | Northern Mechanical | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | New | Infrastructure Cost for PURBBA BANSGAON CHAKLA T/W No. II, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003326724, Reference ID : 403152618] |  |  | BILL/02037/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.12 | 0 | 0 | 0
5 | DARJEELING | Phansidewa | Northern Mechanical | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | New | Infrastructure Cost for PURBBA BANSGAON CHAKLA T/W No. I, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003326733, Reference ID : 403152619] |  |  | BILL/02036/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.64 | 0 | 0 | 0
6 | DARJEELING | Phansidewa | Northern Mechanical | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | New | Additional Charges for New Service Connection at Purba Bansgaon Chakla PWSS ,Zone-II,TW-II under NMD PHEdte. Ref ID- 860316628 Application ID- 100000122188 |  |  | BILL/01455/2024-2025 | BP/24-25/245 | 26/11/2024 | 26/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 22.22 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | New | Construction of 250 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site along with distribution system, functional household tap connection, rising main, pump house (2 nos.), IEP, boundary wall and tubewell under Jal Jeevan Mission of PURBA BANSGAON CHAKLA Piped Water Supply Scheme under Phansidewa Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000108/2023-2024 | 1148/SWSD | 08/08/2023 | 01/10/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 497.64 | 76.24 | 15.32 | 10
8 | DARJEELING | Phansidewa | Northern Mechanical | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I,II & (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000754/2023-2024 | 1582/NMD | 08/09/2023 | 31/08/2025 | M/S SAJAHAN CHOWDHURY | 34.01 | 22.62 | 66.5 | 70
9 | DARJEELING | Phansidewa | Central Drilling | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.47 | 0.06 | 11
Total | [13 empty] | 21948.02 | 116.01 | 0.53