## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Naxalbari | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Kilaram Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000318/2022-2023 | 251/SSD | 12/05/2022 | 01/06/2022 | ENVIROTECH SOLUTIONS | 3.36 | 3.36 | 100 | 0
2 | DARJEELING | Naxalbari | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 205/SWSD | 25/04/2023 | 25/04/2023 | Resource Division | 67.51 | 0 | 0 | 0
3 | DARJEELING | Naxalbari | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 2290/SWSD | 11/12/2023 | 11/12/2023 | Resource Division | 2.9 | 0 | 0 | 0
4 | DARJEELING | Naxalbari | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | New | Construction of 250 cu.m. Capacity R.C.C. Elevated Reservosir, 20 mtrs. Staging height at head works site, laying Rising Main, Laying distribution pipe line with Functional House Hold Tap Connection (FHTC), construction of three numbers Pump House (5.40 m X 3.60 m), 2 (two) nos. Iron Elimination Plant (IEP) with Blower Room Sinking of 3 (three) nos. Tube Well (ODEX-165 method) and Boundary Wall for KILARAM PWSS (Zone-I & II), Block Naxalbari, Dist. Darjeeling under Siliguri W/S Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000112/2023-2024 | 1159/SWSD | 09/08/2023 | 05/04/2024 | RAMESH KUMAR AGARWAL & CO | 645.57 | 293.34 | 45.44 | 55
5 | DARJEELING | Naxalbari | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | New | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 74/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 13.27 | 0 | 0 | 0
6 | DARJEELING | Naxalbari | Northern Mechanical | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | New | New Service Connection Charge for KILARAM, T/W No. I, under NAXALBARI CCC, [APPLICATION NO. 4003313640, Reference ID : 403145711] |  |  | BILL/01972/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.56 | 0 | 0 | 0
7 | DARJEELING | Naxalbari | Northern Mechanical | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | New | New Service Connection Charge for KILARAM, T/W No. II, under NAXALBARI CCC, [APPLICATION NO. 4003313623, Reference ID : 403145716] |  |  | BILL/01970/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.53 | 0 | 0 | 0
8 | DARJEELING | Naxalbari | Northern Mechanical | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | New | New Service Connection Charge for KILARAM, T/W No. III, under NAXALBARI CCC, [APPLICATION NO. 4003313552, Reference ID : 403145729] |  |  | BILL/01971/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.2 | 0 | 0 | 0
9 | DARJEELING | Naxalbari | Central Drilling | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 22089.68 | 296.7 | 1.34