## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Barapathuram Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000326/2022-2023 | 407/SSD | 28/07/2022 | 17/08/2022 | ENVIROTECH SOLUTIONS | 3.99 | 0 | 0 | 100
2 | DARJEELING | Phansidewa | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE., VIVEKANANDA BHAWAN (2ND FLOOR), HILL CART ROAD, SILIGURI FOR THE PERIOD FROM 01.03.2023 TO 31.07.2023 (FOR CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE.) i.e. 5 (FIVE) MONTHS. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000341/2022-2023 | 2645/SWSD | 01/03/2023 | 01/08/2023 | PINKI DAM | 0.74 | 0 | 0 | 40
3 | DARJEELING | Phansidewa | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 2200/SWSD | 04/01/2023 | 04/01/2023 | Resource Division | 85.16 | 0 | 0 | 0
4 | DARJEELING | Phansidewa | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6'00X4'00 size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete(1:2:4) footing size 250X250X600 mm. under ground.The board for display to be made on self-adhesive latex venyle print (UVray protected) 100 micron as per standard format given from department to be pasted over M.S. sheet ( size-6'X4') including carriage , loading ,unloading at different sites under the area of four nos. Blocks under Siliguri Mahakuma Parishad area. Total nos of board -84 nos. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000319/2023-2024 | 641/SWSD | 11/03/2024 | 26/03/2024 | BUDDHADEV NAG | 11.93 | 0 | 0 | 55
5 | DARJEELING | Phansidewa | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 59/SWSD | 09/01/2024 | 09/01/2024 | Resource Division | 22.92 | 0 | 0 | 0
6 | DARJEELING | Phansidewa | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | Infrastructure Cost for BARA PATHURAM, T/W-I,ZONE-II under PHASIDAWA CCC [APPLICATION NO. 4003340843 ; Reference ID : 403163867] |  |  | BILL/02063/2023-2024 | BP/23-24/313 | 28/02/2024 | 28/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.55 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | New Service Connection Charge for BARA PATHURAM, T/W No. I, ZONE-I under PHANSIDAWA CCC, [APPLICATION NO. 4003321578, Reference ID : 403148659] |  |  | BILL/01973/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.26 | 0 | 0 | 0
8 | DARJEELING | Phansidewa | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | Infrastructure Cost for BARA PATHURAM, T/W-I,ZONE-I under PHASIDAWA CCC [APPLICATION NO. 4003340866 , Reference ID : 403163866] |  |  | BILL/02062/2023-2024 | BP/23-24/313 | 28/02/2024 | 28/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.33 | 0 | 0 | 0
9 | DARJEELING | Phansidewa | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | New Service Connection Charge for BARA PATHURAM, T/W No. II, ZONE-I under PHANSIDAWA CCC, [APPLICATION NO. 4003321619, Reference ID : 403148640] |  |  | BILL/01974/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.62 | 0 | 0 | 0
10 | DARJEELING | Phansidewa | Central Drilling | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
11 | DARJEELING | Phansidewa | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | Construction of 250 cu.m. (1 No.) & 150 Cum (2Nos) capacity R.C.C Elevated Reservoir , 20 Mtrs. Stagging Height at the head work site ( Zn-l,Zn-ll & Zn-lll) including distribution system (HDPE) with Rising Main , Rig bore 6 nos big dia T/W by ODEX-165method, Providing Functional Household Connection (FHTC) , Construction of 6 nos. Pump Houses, 3 Nos. Blower Rooms, Boundary walls, Installation of I.E. Plants (Capacity 30,50 & 30 cu.m./hr), Horizontal boring, Soil Testing and allied works at BARA PATHURAM Piped WS Scheme within Phansidewa block, under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000105/2023-2024 | 1131/SWSD | 07/08/2023 | 22/10/2025 | UNIBRO INFRASERV PRIVATE LIMITED | 1076.34 | 0 | 0 | 30
12 | DARJEELING | Phansidewa | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA PATHURAM PIPED WATER SUPPLY SCHEME, ( ZONE-I) TW No. I, II, (ZONE-II) TW No. I, II and (ZONE-III) TW No. I, II, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000791/2023-2024 | 1655/NMD | 29/09/2023 | 10/09/2025 | ALPHA ENTERPRISE | 45.3 | 0 | 0 | 24
Total | [13 empty] | 22604.89 | 0 | 0