## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Central Drilling | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Construction of pump house (3.60 m X 2.40 m) size with sanitary and plumbing arrangement at 2nd tubewell site for Kalkut Piped Water Supply Scheme (Zone-II) under JJM within Matigara Block, Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000094/2023-2024 | 1029/SWSD | 26/07/2023 | 24/09/2023 | PANKAJ KUNDU | 4.58 | 0 | 0 | 0
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-F) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000102/2023-2024 | 1033/SWSD | 26/07/2023 | 09/09/2023 | S.K. BANIK | 9.71 | 0 | 0 | 0
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Construction of boundary wall at 3rd tubewell site of Kalkut Piped Water Supply Scheme (Zone-I) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000087/2023-2024 | 1024/SWSD | 26/07/2023 | 24/09/2023 | SHREYANSH AUTOMOBILE | 7.63 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum Work Order for Construction of boundary wall at 2nd tubewell site of Kalkut Piped Water Supply Scheme (Zone-III) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000089/2023-2024 | 1026/SWSD | 26/07/2023 | 24/09/2023 | M/S SHIB ENTERPRISE | 7.72 | 0 | 0 | 0
6 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Construction of pump house (3.60 m X 2.40 m) size with sanitary and plumbing arrangement at 3rd tubewell site for Kalkut Piped Water Supply Scheme (Zone-III) under JJM within Matigara Block, Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000095/2023-2024 | 1030/SWSD | 26/07/2023 | 24/09/2023 | CHOWDHURY & BASU ENTERPRISE | 4.74 | 0 | 0 | 0
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Construction of boundary wall at 2nd tubewell site of Kalkut Piped Water Supply Scheme (Zone-I) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000085/2023-2024 | 1023/SWSD | 26/07/2023 | 01/04/2025 | S.G.CONSTRUCTION | 7.63 | 0 | 0 | 0
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Construction of 450 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site at KALKUT Piped W/S Scheme (Zone-2) and FHTC Part-J under JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000121/2023-2024 | 1226/SWSD | 14/08/2023 | 30/01/2025 | BUDDHADEV NAG | 164.68 | 97.41 | 59.16 | 1
9 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Construction of boundary wall at 3rd tubewell site of Kalkut Piped Water Supply Scheme (Zone-III) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000090/2023-2024 | 1027/SWSD | 26/07/2023 | 24/09/2023 | S.K. BANIK | 7.63 | 0 | 0 | 0
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Sche me (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-D). | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000124/2023-2024 | 1233/SWSD | 14/08/2023 | 28/09/2023 | ROYAL ENTERPRISE | 9.81 | 0 | 0 | 0
11 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site, Rising main and laying distribution system Part-A at KALKUT Piped W/S Scheme (Zone-I) under JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000136/2023-2024 | 1404/SWSD | 21/08/2023 | 16/09/2026 | M/S G.C. CONSTRUCTION & CO. | 152.43 | 89.96 | 59.02 | 90
12 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Laying distribution system Part-B and allied works at Kalkut Piped W/S Scheme (Zone-I) undere JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000134/2023-2024 | 1373/SWSD | 18/08/2023 | 23/06/2024 | DEBASHIS SINHA | 226.29 | 124.47 | 55.01 | 60
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Laying distribution system along with laying of rising main with interconnection at Kalkut Piped Water Supply Scheme (Zone-III) under JJM at Matigara Block, Darjeeling District, under Siliguri Sub Division, PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000128/2023-2024 | 1241/SWSD | 16/08/2023 | 20/11/2026 | MANAS KUMAR SAHA | 358.73 | 111.45 | 31.07 | 29
14 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for construction of Rig bore big dia deep tubewell by Odex-165 method of drilling at head works, 2nd TW and 3rd TW site of Kalkut Piped Water Supply Scheme (Zone-III) under JJM within Matigara block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000174/2023-2024 | 1736/SWSD | 22/09/2023 | 06/11/2023 | ABHIJIT CHANDA | 21.28 | 0 | 0 | 0
15 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for construction of Rig bore big dia deep tubewell by Odex-165 method of drilling at head works, 2nd TW and 3rd TW site of Kalkut Piped Water Supply Scheme (Zone-II) under JJM within Matigara block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000173/2023-2024 | 1735/SWSD | 22/09/2023 | 06/11/2023 | ABHIJIT CHANDA | 21.28 | 6.81 | 32.01 | 31
16 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Work Order for laying distribution system along with laying of rising main with interconnection at Kalkut Piped Water Supply Scheme (Zone-II) Part-A under JJM Matigara Block, Darjeeling District, under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000179/2023-2024 | 1730/SWSD | 21/09/2023 | 20/12/2023 | ARUN KUMAR SHRIVASTAVA | 111.73 | 0 | 0 | 0
17 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum Work Order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped water Supply Scheme (Zone-II) with Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000184/2023-2024 | 1830/SWSD | 03/10/2023 | 17/11/2023 | KULENDRA NATH BARMAN | 19.02 | 0 | 0 | 0
18 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-B) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000186/2023-2024 | 1883/SWSD | 09/10/2023 | 08/11/2023 | M/S S.P. BISWAS | 4.85 | 0 | 0 | 0
19 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME, (ZONE-II) TW NO I, II, III AND (ZONE-III) TW NO I, II, III in the district of DARJEELING under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000808/2023-2024 | 1665/NMD | 29/09/2023 | 29/10/2023 | ORIENTAL ENGINEERING CO. | 57.97 | 20.78 | 35.85 | 30
20 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance Cum Work Order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-C) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000221/2023-2024 | 2050/SWSD | 07/11/2023 | 07/12/2023 | CHOWDHURY & BASU ENTERPRISE | 4.85 | 0 | 0 | 0
21 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance Cum Work Order for Construction of boundary wall at head work site of Kalkut Piped Water Supply Scheme (Zone-I) with site development and other allied works under JJM within Matigara block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000218/2023-2024 | 2034/SWSD | 06/11/2023 | 05/01/2024 | SANJIB SAHA | 18.35 | 0 | 0 | 0
22 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance Cum Work Order for Providing Functional Household Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000219/2023-2024 | 2035/SWSD | 06/11/2023 | 21/12/2023 | M/S DIBYA CONSTRUCTION | 19.86 | 0 | 0 | 0
23 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-A). | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000100/2023-2024 | 1031/SWSD | 26/07/2023 | 31/05/2025 | A.B. GANAPATI CONSTRUCTION | 4.85 | 0 | 0 | 100
24 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF PIPED KALKUT WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000068/2023-2024 | 261/SSD | 05/06/2023 | 15/06/2023 | ENVIROTECH SOLUTIONS | 4.68 | 4.65 | 99.36 | 100
25 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum Work Order for Construction of boundary wall at 2nd tubewell site of Kalkut Piped Water Supply Scheme (Zone-II) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000088/2023-2024 | 1025/SWSD | 26/07/2023 | 24/09/2023 | A.B. GANAPATI CONSTRUCTION | 7.63 | 0 | 0 | 75
26 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Construction of pump house with toilet at Head Works site of Kalkut Piped Water Supply Scheme (Zone-II) under JJM within Matigaraa Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000091/2023-2024 | 1028/SWSD | 26/07/2023 | 24/09/2023 | PANKAJ KUNDU | 5.63 | 5.63 | 100 | 90
27 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-E) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000101/2023-2024 | 1032/SWSD | 26/07/2023 | 18/05/2026 | S.G.CONSTRUCTION | 9.71 | 0 | 0 | 100
28 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 2285 | 11/12/2023 | 11/12/2023 | Resource Division | 4.28 | 0 | 0 | 0
29 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1801/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 142.4 | 0 | 0 | 0
30 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for providing functional house hold tap connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-I). | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000010/2024-2025 | 1779/SWSD | 12/07/2024 | 26/08/2024 | SWAPAN CHANDRA DAS | 19.86 | 0 | 0 | 0
31 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Construction of 550 cu.m. capacity R.C.C. Elevated, 20 mtrs. Staging height at the head works site and FHTC (Part-C) at KALKUT Piped W/S Scheme (Zone-3) under JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte. (SL No.01) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000127/2024-2025 | 2616/SWSD | 23/09/2024 | 06/05/2025 | BUDDHADEV NAG | 205.05 | 0 | 0 | 60
32 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for construction of boundary wall at head work site of Kalkut piped Water Supply Scheme (Zone-II) with site development and other allied works under JJM within Matigara block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000007/2024-2025 | 1596/SWSD | 25/06/2024 | 31/05/2026 | S.K. BANIK | 18.36 | 0 | 0 | 10
33 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Work order for Laying distribution system at Kalkut Piped Water Supply Scheme (Zone-II) Part-B under JJM at Matigara Block, Darjeeling District, under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000031/2024-2025 | 2026/SWSD | 06/08/2024 | 02/02/2025 | NARENDRA KUMAR | 128.48 | 9.01 | 7.01 | 30
34 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for construction of pump house (3.6 m X 2.40 m) size with sanitary and plumbing arrangement at 2nd tubewell site for Kalkut Piped Water Supply Scheme (Zone-III) under JJM within Matigara Block, Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000256/2023-2024 | 102/SWSD | 15/01/2024 | 01/02/2025 | ARATI SAHA | 4.82 | 4.1 | 85 | 88
35 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | New Service Connection Charge for KALKUT, T/W No. I, ZONE-II, under PRADHAN NAGAR CCC [APPLICATION NO. 4003302654 ; Reference ID : 403132349] |  |  | BILL/01819/2023-2024 | BP/23-24/279 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.49 | 0 | 0 | 0
36 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Charges for new service connection at T.W No-I,zone-III of Kalkut (Aug) w/s scheme in the dist of Darjeeling under NMD PHE dte. |  |  | BILL/00492/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.35 | 0 | 0 | 0
37 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | New Service Connection Charge for KALKUT, T/W No. II, ZONE-II, under PRADHAN NAGAR CCC [APPLICATION NO. 4003302722 ; Reference ID : 4003132350] |  |  | BILL/01818/2023-2024 | BP/23-24/278 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 17.36 | 0 | 0 | 0
38 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | FUEL FOR OFFICE VECHILE OF EXECUTIVE ENGINEER SILIGURI W/S DIVISION PHE DTE |  |  | BILL/00400/2023-2024 | BP-2023-24-161 | 29/01/2024 | 29/01/2024 | SONA PETROL PUMP | 0.3 | 0 | 0 | 0
39 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Charges for new service connection at T.W No-III,zone-II of Kalkut (Aug) w/s scheme in the dist of Darjeeling under NMD PHE dte. |  |  | BILL/00491/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.84 | 0 | 0 | 0
40 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | SHIFTING OF LT INFRASTRUCTURE AT T.W NO-I,Z-III OF AUG KALKUT W/S/S UNDER NMD PHE DTE. |  |  | BILL/01504/2024-2025 | BP/24-25/248 | 06/12/2024 | 06/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.22 | 0 | 0 | 0
41 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) at Kalkut Zone-3 Command area of Augmentation of Kalkut PWSS in connection with JJM under Siliguri W/S Division P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000242/2024-2025 | 483/SWSD | 12/02/2025 | 14/03/2025 | DEBASHIS SINHA | 15.2 | 0 | 0 | 0
42 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-III) under Matigara Block under Siliguri Sub Division, P.H.E.Dte. (Part A). | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000021/2025-2026 | 1403/SWSD | 08/05/2025 | 07/07/2025 | SAFTI PRIVATE LIMITED | 53.44 | 0 | 0 | 0
43 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000995/2024-2025 | 14/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0 | 0
44 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 10/11/2025 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
45 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) at Kalkut Zone-1 Command area of Augmentation of Kalkut PWSS inconnection with JJM under Siliguri W/S Division P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000236/2024-2025 | 243/SWSD | 22/01/2025 | 21/02/2025 | M/S G.C. CONSTRUCTION & CO. | 15.2 | 0 | 0 | 0
46 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) under Augmentation of Kalkut PWSS (Zone-II) under Matigara Block in connection with JJM under Siliguri W/S Division P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000013/2025-2026 | 1239/SWSD | 24/04/2025 | 24/05/2025 | BUDDHADEV NAG | 36.69 | 0 | 0 | 0
47 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Acceptance cum Work Order for Construction of Pump House, Boundary wall, IEP and Blower room and allied work for Augmentation Kalkut Zone-1within Matigara block in connection with JJM under Siliguri W/S Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000016/2025-2026 | 1349/SWSD | 02/05/2025 | 16/06/2025 | BRM DEVELOPERS | 28.42 | 0 | 0 | 0
48 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001065/2024-2025 | 33/NMD | 06/01/2025 | 05/02/2025 | SAIKAT SINHA | 12.3 | 0 | 0 | 0
49 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | Augmentation | Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-III) within Matigara Block under Siliguri Sub Division, P.H.E.Dte. (Part ¿ B). | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000020/2025-2026 | 1094/SWSD | 11/04/2025 | 10/06/2025 | SAFTI PRIVATE LIMITED | 58.79 | 0 | 0 | 0
Total | [13 empty] | 23578.13 | 474.27 | 2.01