## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF KAWAKHALI PIPED WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) |  | ORD/000069/2023-2024 | 262/SSD | 05/06/2023 | 15/06/2023 | ENVIROTECH SOLUTIONS | 4.02 | 3.99 | 99.26 | 100
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1802/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 59.09 | 0 | 0 | 0
3 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | New Service Connection Charge for AUG. OF KAWAKHALI, T/W No. III, under PHANSIDEWA CCC, [APPLICATION NO. 4003317469, Reference ID : 403145877] |  |  | BILL/01975/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.98 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | New Service Connection Charge for AUG KAWAKHALI, T/W No.II, under PHANSIDAWA CCC, [APPLICATION NO. 4003320218, Reference ID : 403148651] |  |  | BILL/01977/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.1 | 0 | 0 | 0
5 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | New Service Connection Charge for AUG KAWAKHALI, T/W No. I, under PHANSIDAWA CCC, [APPLICATION NO. 4003320233, Reference ID : 403148653] |  |  | BILL/01976/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.61 | 0 | 0 | 0
6 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KAWAKHALI PIPED WATER SUPPLY SCHEME, (Zone-II) TW No. I, II and (Zone-III) TW-I, II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000463/2023-2024 | 1439/NMD | 10/08/2023 | 05/04/2025 | ALPHA ENTERPRISE | 47.79 | 1.42 | 2.96 | 75
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | Construction of 250 cu.m. Capacity R.C.C. Elevated Reservoir, 20 Mtrs. Staging Height at the head works site (Zone-II), including Rising Mains, Distribution System Providing Functional household Tapn Connection (FHTC), Iron Elimination Plant (IEP) with Blower Room, Boundary wall & Soil Investigation at H/W site (Zone-II) for Augmentation of KAWAKHALI (Zone-I, II & III) Piped Water Supply Scheme Block : Matigara under Siliguri W/S Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000122/2023-2024 | 1230/SWSD | 14/08/2023 | 01/07/2025 | FAIRDEAL ASSOCIATES | 827.38 | 79.79 | 9.64 | 25
8 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | ACCEPTANCE CUM WORK ORDER FOR CONSTRUCTION OF BOUNDARY WALL AT EXISTING PUMP HOUSE (two nos)FOR KAWA KHALI W/S SCHEME UNDER SILIGURI WATER SUPPLY DIVISION PHE DTE.(CONSIDERING A LENGTH OF 70 METRE) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000239/2024-2025 | 193/SWSD | 16/01/2025 | 02/03/2025 | RAJEEV RANJAN OJHA | 8.04 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000995/2024-2025 | 14/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0 | 0
10 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | CONSTRUCTION OF PATHWAY & LAND DEVOLOPMENT FOR KAWAKHALI ZONE-I , II & III PIPED WATER SUPPLY SCHEME (H/W SITE & 2ND T/W SITE) BLOCK MATIGARA DISTRICT : DARJEELING UNDER SILIGURI W/S DIVISION P.H.E.Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000155/2024-2025 | 2846/SWSD | 23/10/2024 | 22/11/2024 | FAIRDEAL ASSOCIATES | 19.13 | 0 | 0 | 0
11 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001066/2024-2025 | 34/NMD | 06/01/2025 | 05/02/2025 | PRATIK ROY | 9.2 | 0 | 0 | 0
Total | [13 empty] | 1033.13 | 85.19 | 8.25