## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1809/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 193.96 | 0 | 0 | 0
2 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Shyamdhan Zone I (Part D) of the Shyamdhan Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 12. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000082/2022-2023 | 855/SWSD | 21/07/2022 | 15/08/2022 | SWAPAN CHANDRA DAS | 24.77 | 0 | 0 | 40
3 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Shyamdhan Zone I (Part B) of the Shyamdhan Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 10. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000080/2022-2023 | 853/SWSD | 21/07/2022 | 20/08/2022 | PRADIP GUHA | 26.69 | 0 | 0 | 40
4 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Shyamdhan Zone I (Part C) of the Shyamdhan Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 11 | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000081/2022-2023 | 854/SWSD | 21/07/2022 | 15/08/2022 | M/S SHIVAJI ROY | 18.45 | 0 | 0 | 40
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Soil investigation of Shyamdhan Zone- I PWSS for Construction of 300 cum OHR under Siliguri Sub Division, PHE Dte. under Kharibari Block | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000170/2023-2024 | 435/SSD | 12/09/2023 | 02/10/2023 | GEOCON INDIA | 1.03 | 0 | 0 | 100
6 | DARJEELING |  | Central Drilling | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 19/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
7 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Soil investigation of Shyamdhan Zone- II PWSS for Construction of 200 Cum OHR under Siliguri Sub Division, PHE Dte. under Kharibari Block | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000168/2023-2024 | 436/SSD | 12/09/2023 | 02/10/2023 | MABCO CONSULTANT | 1.03 | 0 | 0 | 100
8 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | New Service Connection Charge for SHYAMDHAN, T/W No. II, ZONE-II under KHARIBARI CCC, [APPLICATION NO. 4003320230, Reference ID : 403147069] |  |  | BILL/01980/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.41 | 0 | 0 | 0
9 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | New Service Connection Charge for SHYAMDHAN, T/W No. III, ZONE-I under KHARIBARI CCC, [APPLICATION NO. 4003320066, Reference ID : 403147080] |  |  | BILL/01978/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.42 | 0 | 0 | 0
10 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | New Service Connection Charge for SHYAMDHAN, T/W No. I, ZONE-II under KHARIBARI CCC, [APPLICATION NO. 4003320289, Reference ID : 403147077] |  |  | BILL/01979/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.07 | 0 | 0 | 0
11 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Construction of 300 Cu.M. capacity R.C.C. Elevated Reservoir, 20 Mtrs. Staging Height at the head works site including distribution system with Providing Functional Household Tap Connection (FHTC), construction of Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at 3rd TW site and allied works at distribution pipe line under Jal Swapna/JJM works for Augmentation of Shyamdhan (ZONE-I) Piped Water Supply Scheme (PART-A), Kharibari block under Siliguri Sub Division.P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000082/2023-2024 | 1049/SWSD | 28/07/2023 | 22/09/2025 | M/S BIRAT CONSTRUCTION | 319.92 | 0 | 0 | 40
12 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. III ,& (Zone-II) TW-I,II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000455/2023-2024 | 1394/NMD | 09/08/2023 | 31/08/2025 | WEST BENGAL ENGINEERING CO. | 34.92 | 0 | 0 | 90
13 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Construction of Pump House 2 Nos. (3.65 X 2.45, Zn-II 2nd and 3rd T/W Zn-I) size with (1.20 X 2.10 M) size toilet, plinth protection, 3 nos. Boundary Wall and IEP (40 cu.m/hr. Zn-II H/W, 20 cu.m/hr Zn-I H/W) Supplying, fabrication eretion on suitable RCC foundation and Commissioning with 3 (three) month trial run of pressure type Iron Removal Plant with Blower cum Compressure Room 2 nos. (Zn-II and I, H/W) with required size platform, surface drain at SHYAMDHAN Piped Water Supply Scheme at kharibari block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000146/2023-2024 | 1414/SWSD | 22/08/2023 | 13/02/2025 | KOHINOOR ALAM | 84.29 | 0 | 0 | 40
14 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | Work order for Construction of 200 cu.m capacity R.C.C. Elevated Reservoir, 20 mtrs. staging height at the head work site including pump house (H/W site), rising main and distribution system with providing household tap connection (FHTC), construction of rig bored big dia deep tubewells (H/W & 2nd sites) by ODEX-165 method of drilling and allied works at distribution pipe line under Jal Swapna/JJM works for Augmentation of Shyamdhan Piped Water Supply Scheme (Zone-II), Kharibari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000257/2023-2024 | 107/SWSD | 15/01/2024 | 17/08/2025 | M/S YOUNG ASSOCIATES | 329.38 | 0 | 0 | 35
15 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | Augmentation | CONSTRUCTION OF BOUNDARY WALL, DRAIN, PATHWAY INCLUDING LAND DEVELOPMENT AT HEAD WORK SITE OF SHYAMDHAN ZONE-II AND RENOVATION OF BOUNDARY WALLS, PUMP HOUSES AT H/W SITE AND 2ND SITE OF SHYAMDHAN ZONE-I INCLUDING WASHOUT LINES ICW AUGMENTATION OF SHYAMDHAN PWSS RELATED TO JAL JEEVAN MISSION (JJM) AT KHARIBARI BLOCK WITHIN SILIGURI W/S DIVISION, PHE DTE. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000147/2024-2025 | 2845/SWSD | 23/10/2024 | 18/09/2025 | D S ENTERPRISE | 43.07 | 0 | 0 | 30
Total | [13 empty] | 1163.1 | 0 | 0