## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Kashiram Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000319/2022-2023 | 255/SSD | 17/05/2022 | 06/06/2022 | ENVIROTECH SOLUTIONS | 4.05 | 4 | 98.76 | 100
2 | DARJEELING | Phansidewa | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 2291/SWSD | 11/12/2023 | 11/12/2023 | Resource Division | 1.63 | 0 | 0 | 0
3 | DARJEELING | Phansidewa | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1805/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 7 | 0 | 0 | 0
4 | DARJEELING | Phansidewa | Northern Mechanical | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KASHIRAM PIPED WATER SUPPLY SCHEME, TW No.- I,II and III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000789/2023-2024 | 1653/NMD | 29/09/2023 | 29/10/2023 | SUNRISE ENGINEERING CORPORATION | 23 | 0 | 0 | 0
5 | DARJEELING | Phansidewa | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 78/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 22.19 | 0 | 0 | 0
6 | DARJEELING | Phansidewa | Northern Mechanical | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | Quotation Charges New service Connection at Kashiram PWSS,TW-III under NMD,PHE Dte. Application No - 4003458955 Ref Id- 403256880 |  |  | BILL/00832/2024-2025 | BP/24-25/157 | 07/08/2024 | 07/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 20.61 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Northern Mechanical | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | New Service Connection Charge for KASHIRAM , T/W No. II under PHANSIDAWA CCC, [APPLICATION NO. 4003317760, Reference ID : 403145866] |  |  | BILL/01982/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.26 | 0 | 0 | 0
8 | DARJEELING | Phansidewa | Northern Mechanical | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | New Service Connection Charge for KASHIRAM , T/W No. I under PHANSIDAWA CCC, [APPLICATION NO. 4003317755, Reference ID : 403145742] |  |  | BILL/01981/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.28 | 0 | 0 | 0
9 | DARJEELING | Phansidewa | Central Drilling | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 12.52 | 0.06 | 11
10 | DARJEELING | Phansidewa | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | New | Construction of 350 cu.m. Capacity Elevated Reservoir 20 m staging height allied with laying of distribution pipeline, Rising Main,construction of 3 nos. Big dia rig bore tube well by ODEX-165, Pump House, Iron Elemination Plant, Boundary Wall including Functiopnal Household Tap Connection at KASHIRAM Piped Water Supply Scheme (Zone I & II) undere Phansidewa block, Darjeeling dist. in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000131/2023-2024 | 1366/SWSD | 18/08/2023 | 15/04/2025 | UNIBRO INFRASERV PRIVATE LIMITED | 676.79 | 339.87 | 50.22 | 35
Total | [13 empty] | 22109.59 | 356.4 | 1.61