## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Northern Mechanical | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/18614 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MEHERULLA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II & (Zone-II) TW No. I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000752/2023-2024 | 1580/NMD | 08/09/2023 | 08/10/2023 | B.B. CONCERNED | 34.74 | 0 | 0 | 70
2 | DARJEELING | Phansidewa | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/18614 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Meherulla Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000325/2022-2023 | 403/SSD | 27/07/2022 | 16/08/2022 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 0 | 100
3 | DARJEELING | Phansidewa | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/18614 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1806/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 77.11 | 0 | 0 | 0
4 | DARJEELING | Phansidewa | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/18614 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6'00X4'00 size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete(1:2:4) footing size 250X250X600 mm. under ground.The board for display to be made on self-adhesive latex venyle print (UVray protected) 100 micron as per standard format given from department to be pasted over M.S. sheet ( size-6'X4') including carriage , loading ,unloading at different sites under the area of four nos. Blocks under Siliguri Mahakuma Parishad area. Total nos of board -84 nos. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000319/2023-2024 | 641/SWSD | 11/03/2024 | 26/03/2024 | BUDDHADEV NAG | 11.93 | 0 | 0 | 55
5 | DARJEELING | Phansidewa | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/18614 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 82/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 10.77 | 0 | 0 | 0
6 | DARJEELING | Phansidewa | Central Drilling | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/18614 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
7 | DARJEELING | Phansidewa | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/18614 | New | Construction of 250 cu.m. capacity R.C.C. Elevated Reservoir, 20 Mtrs. Staging Height at the head works site along with distribution system, functional household tap connection, rising main, pump house (4 nos.), IEP, Bounary wall, tubewell and soil investigation under Jal Jeevan Mission at MEHERULLA Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000314/2023-2024 | 545/SWSD | 01/03/2024 | 26/03/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 626.06 | 0 | 0 | 25
Total | [13 empty] | 22103.92 | 0 | 0