## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME | SM/18637 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 2233/SWSD | 06/01/2023 | 06/01/2023 | Resource Division | 199.97 | 0 | 0 | 0
2 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME | SM/18637 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME, (Zone-I) TW No. I,II & (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000750/2023-2024 | 1578/NMD | 08/09/2023 | 08/10/2023 | M/S RATAN KUMAR DASGUPTA AND CO. | 34.71 | 20.76 | 59.81 | 85
3 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME | SM/18637 | Augmentation | New Service Connection Charge for AUG. OF RANIDANGA RANGAPANI, T/W No. II, under PHANSIDEWA CCC [APPLICATION NO. 4003314400 ; Reference ID : 403144139] |  |  | BILL/01812/2023-2024 | BP/23-24/281 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.2 | 0 | 0 | 0
4 | DARJEELING |  | Northern Mechanical | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME | SM/18637 | Augmentation | New Service Connection Charge for RANIDANGA RANGAPANI (AUG), T under PHANSIDEWA CCC , [APPLICATION NO. 4003282303, Reference ID : 403118284] |  |  | BILL/02042/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.85 | 0 | 0 | 0
5 | DARJEELING |  | Siliguri W/S Division | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME | SM/18637 | Augmentation | Construction of 2 Nos. 250 Cu.M capacity Elevated Reservoir 20m staging height allied with laying of distribution pipeline, Rising Mains, construction of Big dia rig bore tube wells by ODEX - 165, Pump Houses (5.4 x 3.60 m & 3.6 x 3.0 m ) , Iron Elemination Plants , Boundary Walls including Functional Household Tap Connections for Augmentation of RANIDANGA AND RANGAPANI Piped Water Supply Scheme (Zone -I and Zone - II) under Naxalbari Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000127/2023-2024 | 1240/SWSD | 16/08/2023 | 01/02/2025 | THE MAHADEV CONSTRUCTION | 1148.16 | 312.65 | 27.23 | 42
6 | DARJEELING |  | Central Drilling | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME | SM/18637 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 5.36 | 0.03 | 11
Total | [13 empty] | 22733.65 | 338.76 | 1.49