## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Phansidewa | Central Drilling | Mandila Jhar Piped Water Supply Scheme. | SM/18784 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 5.98 | 0.03 | 11
2 | DARJEELING | Phansidewa | Siliguri W/S Division | Mandila Jhar Piped Water Supply Scheme. | SM/18784 | New | Work Order for Construction of 250 cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging height at the head work site including distribution system (HDPE) with rising main, Rig bore 2 nos. big dia T/W by Odex-165 method, providing functional household tap connection (FHTC), pump house 2 nos., blower room, IEP 60 cu.m./hr., boundary walls, soil testing and allied works at Mandilajhar PWSS Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000183/2023-2024 | 1812/SWSD | 03/10/2023 | 30/10/2024 | KRISHNA TRADING CO. | 509.14 | 246.14 | 48.34 | 60
3 | DARJEELING | Phansidewa | Northern Mechanical | Mandila Jhar Piped Water Supply Scheme. | SM/18784 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MANDILA JHAR PIPED WATER SUPPLY SCHEME, TW No. I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000938/2023-2024 | 1671/NMD | 29/09/2023 | 01/01/2025 | SAIKAT SINHA | 11.58 | 7.89 | 68.17 | 100
4 | DARJEELING | Phansidewa | Siliguri W/S Division | Mandila Jhar Piped Water Supply Scheme. | SM/18784 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1807/SWSD | 30/09/2023 | 30/09/2023 | Resource Division | 18.81 | 0 | 0 | 0
5 | DARJEELING | Phansidewa | Siliguri W/S Division | Mandila Jhar Piped Water Supply Scheme. | SM/18784 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 76/SWSD | 10/01/2024 | 10/01/2024 | Resource Division | 9.49 | 0 | 0 | 0
6 | DARJEELING | Phansidewa | Northern Mechanical | Mandila Jhar Piped Water Supply Scheme. | SM/18784 | New | Infrastructure Cost for MANDILA JHAR T/W No. II, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322508, Reference ID : 403149170] |  |  | BILL/02044/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.46 | 0 | 0 | 0
7 | DARJEELING | Phansidewa | Northern Mechanical | Mandila Jhar Piped Water Supply Scheme. | SM/18784 | New | Infrastructure Cost for MANDILA JHAR T/W No. I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322513, Reference ID : 403149165] |  |  | BILL/02043/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.51 | 0 | 0 | 0
Total | [13 empty] | 21900.76 | 260.01 | 1.19