## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Procurement of Chemicals & Consumables, Glassware etc. | SM/06616 | Support-WQMSP | Conducting field survey of school, Anganwadis, Health Center and other Government Institutions and updating the existing WASH facilities at the institution in IMIS portal and WBPHED app in various Block's in hill area of kalimpong & Darjeeling District, under 100 days campaign of JJM & Jal Sawpno programme, under Neorakhola W/S & Mtc. Div, PHE Dte Kalimpong. |  |  | ORD/000055/2020-2021 | 254/NKWSMD | 16/12/2020 | 31/12/2020 | SANJOY GURUNG | 1.69 | 3.22 | 190.98 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Procurement of Chemicals & Consumables, Glassware etc. | SM/06616 | Support-WQMSP | Water Sample collection from school, Anganwadis, Health Center and other Government Institutions in various Block's in hill area of kalimpong District, under 100 days campaign of JJM & Jal Sawpno programme, under Neorakhola W/S & Mtc. Div, PHE Dte Kalimpong. |  |  | ORD/000057/2020-2021 | 295/NKWSMD | 25/01/2021 | 24/02/2021 | GLOBAL ENTERPRISE | 3.82 | 6.63 | 173.65 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Procurement of Chemicals & Consumables, Glassware etc. | SM/06616 | Support-WQMSP | Water Sample collection from school, Anganwadis, Health Center and other Government Institutions in various Block's in hill area of Darjeeling District, under 100 days campaign of JJM & Jal Sawpno programme, under Neorakhola W/S & Mtc. Div, PHE Dte Kalimpong. |  |  | ORD/000058/2020-2021 | 296/NKWSMD | 25/01/2021 | 24/02/2021 | SANJOY GURUNG | 4.58 | 9.16 | 200 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Procurement of Chemicals & Consumables, Glassware etc. | SM/06616 | Support-WQMSP | Requirement of Chemicals and glasswares for performing tests of water sample colleceted from AWC, Schools ,Healthcenters under 100 days days Campaign under JJM programme & Jal-Sapna Programme | Assistant Engineer I | Junior Engineer III | ORD/000064/2020-2021 | 365/NKWSMD | 11/02/2021 | 13/03/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.79 | 5.58 | 200 | 0
Total | [13 empty] | 12.87 | 24.59 | 191