## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Conducting field survey of schools, Anganwadis, Health Centres, GP Buildings and Ashramsalas in the hilly district of Darjeeling & Kalimpong comprising 5 nos of block in the district of Darjeeling and 3 nos of blocks in the district of Kalimpong with a vi | SM/10139 | Support-M&E | Creating gravity based Provision Of Drinking water from spring water source for Fangtar primary school in Yangmakum G.P under Kalimpong Block 1 in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000155/2021-2022 | 592/NKWSMD | 10/02/2022 | 12/03/2022 | THE ELECTRIC SPHERE | 3 | 2.72 | 90.63 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Conducting field survey of schools, Anganwadis, Health Centres, GP Buildings and Ashramsalas in the hilly district of Darjeeling & Kalimpong comprising 5 nos of block in the district of Darjeeling and 3 nos of blocks in the district of Kalimpong with a vi | SM/10139 | Support-M&E | Creating gravity based Provision Of Drinking water from spring water source for Fangtar primary school in Yangmakum G.P under Kalimpong Block 1 in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000155/2021-2022 | 592/NKWSMD | 10/02/2022 | 12/03/2022 | THE ELECTRIC SPHERE | 3 | 2.72 | 90.63 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Conducting field survey of schools, Anganwadis, Health Centres, GP Buildings and Ashramsalas in the hilly district of Darjeeling & Kalimpong comprising 5 nos of block in the district of Darjeeling and 3 nos of blocks in the district of Kalimpong with a vi | SM/10139 | Support-M&E | Creating gravity based Provision Of Drinking water from spring water source for Makum Goan primary school in Yangmakum G.P under Kalimpong Block 1 in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000153/2021-2022 | 590/ NKWSMD | 10/02/2022 | 12/03/2022 | RINZING DORJEE MOKTAN | 1.47 | 0 | 0 | 0
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Conducting field survey of schools, Anganwadis, Health Centres, GP Buildings and Ashramsalas in the hilly district of Darjeeling & Kalimpong comprising 5 nos of block in the district of Darjeeling and 3 nos of blocks in the district of Kalimpong with a vi | SM/10139 | Support-M&E | Creating gravity based Provision Of Drinking water from spring water source for Makum Goan primary school in Yangmakum G.P under Kalimpong Block 1 in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000153/2021-2022 | 590/ NKWSMD | 10/02/2022 | 12/03/2022 | RINZING DORJEE MOKTAN | 1.47 | 0 | 0 | 0
5 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Conducting field survey of schools, Anganwadis, Health Centres, GP Buildings and Ashramsalas in the hilly district of Darjeeling & Kalimpong comprising 5 nos of block in the district of Darjeeling and 3 nos of blocks in the district of Kalimpong with a vi | SM/10139 | Support-M&E | Creating gravity based Provision Of Drinking water from spring water source for Panbu primary school in Yangmakum G.P under Kalimpong Block 1 in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. |  | Junior Engineer IV | ORD/000154/2021-2022 | 591/NKWSMD | 10/02/2022 | 12/03/2022 | HEMANT MOKTAN | 3.62 | 3.28 | 90.62 | 0
6 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Conducting field survey of schools, Anganwadis, Health Centres, GP Buildings and Ashramsalas in the hilly district of Darjeeling & Kalimpong comprising 5 nos of block in the district of Darjeeling and 3 nos of blocks in the district of Kalimpong with a vi | SM/10139 | Support-M&E | Creating gravity based Provision Of Drinking water from spring water source for Panbu primary school in Yangmakum G.P under Kalimpong Block 1 in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. |  | Junior Engineer IV | ORD/000154/2021-2022 | 591/NKWSMD | 10/02/2022 | 12/03/2022 | HEMANT MOKTAN | 3.62 | 3.28 | 90.62 | 0
7 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Conducting field survey of schools, Anganwadis, Health Centres, GP Buildings and Ashramsalas in the hilly district of Darjeeling & Kalimpong comprising 5 nos of block in the district of Darjeeling and 3 nos of blocks in the district of Kalimpong with a vi | SM/10139 | Support-M&E | Creating gravity based Provision Of Drinking water from spring water source for Jarayotar tar primary school in Yangmakum G.P under Kalimpong Block 1 in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000152/2021-2022 | 589/NKWSMD | 10/02/2022 | 12/03/2022 | RINZING DORJEE MOKTAN | 1.41 | 1.4 | 98.79 | 0
8 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Conducting field survey of schools, Anganwadis, Health Centres, GP Buildings and Ashramsalas in the hilly district of Darjeeling & Kalimpong comprising 5 nos of block in the district of Darjeeling and 3 nos of blocks in the district of Kalimpong with a vi | SM/10139 | Support-M&E | Creating gravity based Provision Of Drinking water from spring water source for Jarayotar tar primary school in Yangmakum G.P under Kalimpong Block 1 in the District of kalimpong under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000152/2021-2022 | 589/NKWSMD | 10/02/2022 | 12/03/2022 | RINZING DORJEE MOKTAN | 1.41 | 1.4 | 98.79 | 0
Total | [13 empty] | 19 | 14.78 | 77.8