## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. | SM/10622 | Disaster | Permanent restoration and repair of pipeline track due to Landside triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Thockchu towards Delo Middle Army lake (Betweeen Chain No - 158 to 159) (Betweeen Chain No - 185 to 186) & (Chain No - 360&352) under Neorakhola W/S & Mtc. Division, P.H. E. Dte, Kalimpong | Assistant Engineer II | Junior Engineer IV | ORD/000010/2022-2023 | 109/NKWSMD | 13/04/2022 | 10/10/2022 | JUSTINE BHUTIA | 97.16 | 96.81 | 99.64 | 100
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. | SM/10622 | Disaster | Permanent restoration of pipeline and pipeline track protection work on the eastern and the western side of the Lava lake by Jhora training along with relaying of pipeline of 406.4 mm (O.D) MSERW pipeline damaged due to incessant rainfall of monsoon under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000287/2022-2023 | 1956/NKWSMD | 20/12/2022 | 18/06/2023 | BHUTIA AND SONS | 97.78 | 93.91 | 96.05 | 50
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. | SM/10622 | Disaster | Permanent restoration of approach stair including providing chequrred tiles, concrete pavers and protection walls in the shade area and protection walls on hill side and valley side of the approach road to open ground reservoir at Lava along with laying of pipe line of 406.4 mm (O.D) MSERW pipeline at of Lava OGR, Lava, Kalimpong under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000289/2022-2023 | 1959/NKWSMD | 20/12/2022 | 18/06/2023 | THUPDEN BHUTIA | 74.36 | 74.28 | 99.9 | 50
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. | SM/10622 | Disaster | Permanent restoration of Guard Shed, brick boundry walls and chain link fencing along Lava Gorubathan road along with laying of pipe line of 406.4 mm (O.D) MSERW along with fitting of valves at outlet head works site of Lava OGR, Lava. Kalimpong under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000288/2022-2023 | 1957/NKWSMD | 20/12/2022 | 18/06/2023 | THUPDEN BHUTIA | 78.38 | 70.67 | 90.16 | 100
Total | [13 empty] | 347.68 | 335.67 | 96.55