## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M | SM/10687 | School | Creating gravity based Provision Of Drinking water from spring water source for 79 numbers of school under Kurseong Sub-Division in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte TSM No. 009890 |  | Junior Engineer IV | ORD/000023/2022-2023 | 255/NKWSMD | 06/05/2022 | 02/11/2022 | GARGO TRADERS | 211.58 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M | SM/10687 | School | CREATING GRAVITY BASED PROVISION OF DRINKING WATER FROM SPRING WATER SOURCE FOR 93 NOS OF SCHOOL, 23 NOS OF ICDS CENTRES, 11 NOS OF HEALTH CENTRES, 8 NOS OF GRAM PANCHAYAT IN UNDER RANGLI RANGLIOT BLOCK IN THE DISTRICT OF DARJEELING UNDER NEORAKHOLA WATER SUPPLY DIVISION ,KALIMPONG PHE DTE. TSM No. 009891 | Assistant Engineer I | Junior Engineer I | ORD/000022/2022-2023 | 254/NKWSMD | 06/05/2022 | 02/11/2022 | GARGO TRADERS | 320.59 | 217 | 67.69 | 100
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M | SM/10687 | School | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/04/2024 TO 30/06/2024 (3 MONTHS). | Assistant Engineer I | Junior Engineer III | ORD/000290/2023-2024 | 705/NKWSMD | 27/03/2024 | 27/06/2024 | NIM TSHERING LEPCHA | 3.19 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M | SM/10687 | School | Additional works in various institutes in connection with creating gravity based provision of drinking water from spring water source for 15 number of schools, 06 no of ICDS Centers, 02 Number of Health Centers, 01 Number of Gram Panchayat under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply and Maintenance Division Public Health Engineering Directorate. | Assistant Engineer I | Junior Engineer I | ORD/000405/2022-2023 | 1177/NKWSMD | 18/08/2022 | 17/09/2022 | GARGO TRADERS | 4.85 | 0 | 0 | 100
Total | [13 empty] | 540.21 | 217 | 40.17