## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation and Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos |  |  | VCH/000268/2022-2023 | BP-200 and 201 | 08/11/2022 | 08/11/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 24.64 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos |  |  | VCH/000093/2022-2023 | BP-2022-23-86 | 30/06/2022 | 30/06/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 97 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | SM/10732 | Support-M&E | Preparation of DPR in line with the technical requirement of jal jiwan mission in GTA area |  |  | VCH/000131/2022-2023 | BP-2022-23-115 | 12/08/2022 | 12/08/2022 | RADIANT | 61.53 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos |  |  | VCH/000134/2022-2023 | BP-2022-23-124 | 30/08/2022 | 30/08/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 49.12 | 0 | 0 | 0
5 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | SM/10732 | Support-M&E | Preparation of DPR in line with the technical requirement of jal jiwan mission in GTA area |  |  | VCH/000092/2022-2023 | BP-2022-23-84 | 30/06/2022 | 30/06/2022 | RADIANT | 19.77 | 0 | 0 | 0
6 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos |  |  | VCH/000207/2022-2023 | BP-2022-23-150 | 30/09/2022 | 30/09/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 47 | 0 | 0 | 0
7 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation and Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos |  |  | VCH/000267/2022-2023 | BP-2022-23-198 | 08/11/2022 | 08/11/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 72 | 0 | 0 | 0
8 | DARJEELING |  | Resource | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | SM/10732 | Support-M&E | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 343.17 | 6.24 | 80
Total | [13 empty] | 5871.06 | 343.17 | 5.85