## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division | SM/10765 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000183/2022-2023 | 2575/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 0.84 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division | SM/10765 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 1261/NKWSMD | 05/09/2022 | 05/09/2022 | Resource Division | 0.84 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division | SM/10765 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Soom 2nd Division Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009296 SM Code-SM/08936 |  |  | ORD/000059/2022-2023 | 555/NKWSMD | 26/05/2022 | 25/07/2022 | NAVRATNA CONSTRUCTION CO | 16.91 | 0 | 0 | 100
Total | [13 empty] | 18.59 | 0 | 0