## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection at PWS scheme for Bhotay Goth | SM/10766 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Bhotay Goth, Soom Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009297 SM Code-SM/08931 |  |  | ORD/000042/2022-2023 | 524/NKWSMD | 25/05/2022 | 24/07/2022 | RAMESH PRADHAN AND CO. | 6.23 | 5.62 | 90.21 | 100
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection at PWS scheme for Bhotay Goth | SM/10766 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 1264/NKWSMD | 05/09/2022 | 05/09/2022 | Resource Division | 0.22 | 0 | 0 | 0
Total | [13 empty] | 6.44 | 5.62 | 87.2