## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap connection at PWS scheme for Soom 3rd Division | SM/10767 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Bhotay Goth, Soom 3rd Division Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009298 SM Code-SM/08938 |  |  | ORD/000030/2022-2023 | 493/NKWSMD | 24/05/2022 | 23/07/2022 | MS JAGANNATH PRASAD | 14.04 | 0 | 0 | 98
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap connection at PWS scheme for Soom 3rd Division | SM/10767 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 1260/NKWSMD | 05/09/2022 | 05/09/2022 | Resource Division | 0.8 | 0 | 0 | 0
Total | [13 empty] | 14.84 | 0 | 0