## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Gorukatta | SM/10768 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 1259/NKWSMD | 05/09/2022 |  | Resource Division | 0.78 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Gorukatta | SM/10768 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Gorkata Gram Panchyat -Goke-II , Block Darjeeling -Pull-Bijanbari Block. TSM No. 009301 SM Code-SM/08933 |  |  | ORD/000031/2022-2023 | 494/NKWSMD | 24/05/2022 | 23/07/2022 | MS D.R ENTERPRISES | 24.24 | 16.22 | 66.93 | 100
Total | [13 empty] | 25.02 | 16.22 | 64.84