## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWS at Gorkhey Forest Village | SM/10770 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 1262/NKWSMD | 05/09/2022 | 05/09/2022 | Resource Division | 0.24 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWS at Gorkhey Forest Village | SM/10770 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Gorkhey Forest Villa, Gram Panchyat -Sirkhola Danra Gaon, Block Bijanbari -PullBazar. TSM No. 009469 SM Code-SM/08929 |  |  | ORD/000032/2022-2023 | 495/NKWSMD | 24/05/2022 | 23/07/2022 | NIMA SHERPA | 16.74 | 15.75 | 94.09 | 100
Total | [13 empty] | 16.98 | 15.75 | 92.76