## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. | SM/10774 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Danra Goan, Soom 1st Division, Gram Panchyat -Soom Singtam, Block Bijanbari -PullBazar. TSM No. 009476 SM Code-SM/08937 |  |  | ORD/000060/2022-2023 | 556/NKWSMD | 26/05/2022 | 25/07/2022 | NAVRATNA CONSTRUCTION CO | 16.53 | 0 | 0 | 100
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. | SM/10774 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000124/2022-2023 | 1900/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 0.36 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. | SM/10774 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000184/2022-2023 | 2579/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 0.36 | 0 | 0 | 0
Total | [13 empty] | 17.26 | 0 | 0