## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/10785 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Chunabatti Sub-Center and Ghayabari Primary Health Center, under Kurseong- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000194/2022-2023 | 968/NKWSMD | 12/07/2022 | 11/08/2022 | KAMAKHYA CONSTRUCTION | 4.2 | 0 | 0 | 100
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/10785 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Ghayabari Sub-Center and Mahanadi Sub-Center, under Kurseong- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000195/2022-2023 | 969/NKWSMD | 12/07/2022 | 11/08/2022 | KAMAKHYA CONSTRUCTION | 4.44 | 0 | 0 | 100
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/10785 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Singell Sub-Center & Giddah Pahar Sub-Center, under Kurseong- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000196/2022-2023 | 970/NKWSMD | 12/07/2022 | 11/08/2022 | KAMAKHYA CONSTRUCTION | 4.25 | 0 | 0 | 100
Total | [13 empty] | 12.89 | 0 | 0