## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong,Mirik | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | New | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER KURSEONG, MIRIK BLOCK, DISTRICT OF DARJEELING. [TSM NO -10472] 1. Sukna Forest(Sukna Forest South). 2. Choklong Forest. 3. Panighata(panighata 14 number ward, 10 number line). 4. PanthabariForest(Naya Basti 1). 5. Panthabari Forest(Naya Basti 3). |  |  | ORD/000085/2022-2023 | 607/NKWSMD | 26/05/2022 | 10/09/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 242.87 | 143.47 | 59.07 | 100
2 | DARJEELING | Kurseong,Mirik | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | New | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 1291/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 2.35 | 0 | 0 | 0
3 | DARJEELING | Kurseong,Mirik | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | New | Material Requisition To Resource Division |  |  | RTOR000154/2022-2023 | 2372/NKWSMD | 03/02/2023 | 03/02/2023 | Resource Division | 2.35 | 0 | 0 | 0
4 | DARJEELING | Kurseong,Mirik | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | New | Quotation of wbsedcl for electrical service connection |  |  | BILL/00167/2023-2024 | BP-2023-24-123 | 27/07/2023 | 27/07/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
5 | DARJEELING | Kurseong,Mirik | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | New | Quotation of wbsedcl for electrical service connection |  |  | BILL/00169/2023-2024 | BP-2023-24-125 | 28/07/2023 | 28/07/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
6 | DARJEELING | Kurseong,Mirik | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | New | Quotation of wbsedcl for electrical service connection |  |  | BILL/00168/2023-2024 | BP-2023-24-124 | 27/07/2023 | 27/07/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
7 | DARJEELING | Kurseong,Mirik | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | New | Quotation of wbsedcl for electrical service connection |  |  | BILL/00170/2023-2024 | BP-2023-24-126 | 27/07/2023 | 27/07/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
8 | DARJEELING | Kurseong,Mirik | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | New | Quotation of wbsedcl for electrical service connection |  |  | BILL/00171/2023-2024 | BP-2023-24-122 | 27/07/2023 | 27/07/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
9 | DARJEELING | Kurseong,Mirik | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | New | Mini Piped Water Supply Scheme for South Sukna and Choklong under Kurseong Division. Scheme Code - 10788 TSM/010472 |  |  | BILL/00092/2024-2025 | "BP-2024-25-99 | 08/07/2024 | 08/07/2024 | DIVISIONAL FOREST OFFICER | 4.91 | 0 | 0 | 0
Total | [13 empty] | 252.93 | 143.47 | 56.72