## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA | SM/10798 | New | SURFACE WATER BASED SANTA BHAWAN & RAJBARI LOWER PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. |  |  | ORD/000219/2022-2023 | 1117/NKWSMD | 05/08/2022 | 12/11/2025 | BOBBY PRADHAN | 117.24 | 12.11 | 10.33 | 50
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA | SM/10798 | New | Material Requisition To Resource Division |  |  | RTOR000148/2022-2023 | 2068/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 1.04 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA | SM/10798 | New | ADDITIONAL WORK FOR SANTA BHAWAN & RAJBARI LOWER PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED |  |  | ORD/000368/2025-2026 | 802/NKWSMD | 03/06/2025 | 30/11/2025 | EVERSHINE CONSTRUCTION | 61.28 | 0 | 0 | 0
Total | [13 empty] | 179.56 | 12.11 | 6.75