## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindhuria Goliapakha under Kurseong Sub Division ,PHED,GTA | SM/10801 | New | Material Requisition To Resource Division |  |  | RTOR000266/2022-2023 | 2838/NKWSMD | 17/03/2023 |  | Resource Division | 0.92 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindhuria Goliapakha under Kurseong Sub Division ,PHED,GTA | SM/10801 | New | SURFACE WATER BASED TINDHURIA GOLIAPAKHA PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E-GTA. |  |  | ORD/000220/2022-2023 | 1118/NKWSMD | 05/08/2022 | 01/02/2023 | PREM CHANDRA RAI | 99.95 | 52.16 | 52.19 | 90
Total | [13 empty] | 100.88 | 52.16 | 51.71