## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | SM/10802 | New | SURFACE WATER BASED GHAYABARI PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000080/2022-2023 | 605/NKWSMD | 26/05/2022 | 01/03/2025 | NAVRATNA CONSTRUCTION CO | 125.67 | 44.18 | 35.16 | 90
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | SM/10802 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | SM/10802 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | SM/10802 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR GHAYABARI UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED |  |  | ORD/000370/2025-2026 | 819/NKWSMD | 04/06/2025 | 02/09/2025 | TIKARAM SHARMA | 40.28 | 0 | 0 | 0
Total | [13 empty] | 394.89 | 44.18 | 11.19