## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | SM/10802 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | SM/10802 | New | SURFACE WATER BASED GHAYABARI PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000080/2022-2023 | 605/NKWSMD | 26/05/2022 | 01/03/2025 | NAVRATNA CONSTRUCTION CO | 125.67 | 0 | 0 | 90
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | SM/10802 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
Total | [13 empty] | 354.6 | 0 | 0