## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA | SM/10803 | New | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 2056/NKWSMD | 05/01/2023 |  | Resource Division | 0.57 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA | SM/10803 | New | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 1315/NKWSMD | 09/09/2022 |  | Resource Division | 0.57 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA | SM/10803 | New | SURFACE WATER BASED MARCHEBUNG PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHED-GTA. |  |  | ORD/000079/2022-2023 | 602/NKWSMD | 26/05/2022 | 25/07/2022 | ROSHAN BISWAKARMA | 60.38 | 22.6 | 37.43 | 100
Total | [13 empty] | 61.51 | 22.6 | 36.74