## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Mani Khope under Kurseong Sub Division ,PHED,GTA | SM/10805 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 1066/NKWSMD | 13/09/2023 |  | Resource Division | 0.42 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Mani Khope under Kurseong Sub Division ,PHED,GTA | SM/10805 | New | SURFACE WATER BASED MANI KHOPE PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000268/2022-2023 | 1749/NKWSMD | 25/11/2022 | 23/02/2023 | ROSHAN BISWAKARMA | 78.65 | 34.79 | 44.24 | 100
Total | [13 empty] | 79.07 | 34.79 | 44